DRC

Terms of Reference (TOR)

for

VAT assessment

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and  supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

The overall purpose of this consultancy is analysing and assessing the current VAT process in DRC (HQ only) as well as advising DRC about the treatment of VAT in general, but in particular about reverse charge VAT and VAT compensation.

This will be done by performing mapping the current setup and VAT treatment with relevant stakeholders and comparing these with our needs. This should end up with a conclusion on how we treat VAT going forward.

# Background

DRC is partly exempt from VAT and each year we apply for VAT compensation from the available funds determined by the Danish authorities. The current process is manual and very time consuming.

We generally post VAT directly to our projects (P&L) and then we recover as much as we can once a year in the VAT compensation. However, we suspect, that we are recovering less than we are entitled to, because there is no clear overview of the VAT booked in our ERP system.

We are experiencing an increase in the number of invoices with reverse charge VAT and the tax codes in our ERP system are not set up properly. In order to set this up, we need to assess the requirements.

# Objective of the consultancy

The objective of this consultancy is to analyse and assess our current VAT process and streamline the entire process in order to be VAT compliant and set up the mapping of VAT, so it fits our ERP system and our requirements. More precisely, the consultant is expected to provide an overview of the current VAT legal requirements so we can better understand and treat VAT in an NGO context. This includes but is not limited to VAT compensation, reverse charge VAT, local VAT, foreign VAT.

# Scope of work and Methodology

The Consultant will be required to analyse and understand our current processes. This will be done by meeting with stakeholders in DRC headquarter. After mapping the current processes and our requirements, it’s expected that the Consultant delivers a report concluding the best possible solutions.

# Deliverables

The Consultant will submit a report based on the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1 Review | Desk review | Stakeholder mapping. Data collection. Arrange meetings with stakeholders | 2 working days |
| Phase 2 Analysis | Research and analysis | Analysing the data and inputs from stakeholders. Comparing data to our new requirements and VAT legislation. | 2 working days |
| Phase 3 Reporting | Final report | Prepare report concluding the necessity for changes and where to optimize our processes, based on the analysis. | 3 working days |

The Consultant will provide the documentation by email / Word, Excel, PowerPoint, PDF, etc.<

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 7 working days.

The consultant shall be prepared to complete the assignment no later than 30.09.2023.

# Eligibility, qualification, and experience required

## Essential:

- Extensive knowledge about the VAT compensation model.

- Experience with VAT in an NGO context.

- Knowledge about VAT of goods and service purchased from outside Denmark (Reverse Charge)

- Eligibility:

  - The consultant has to work for a certified auditor.

- Qualification:

  - Educational level: Minimum Cand.merc.aud

- Experience:

  - A minimum of 5 years experience working with VAT.

- Language requirements:

  - Written and spoken fluency in Danish

  - Speaking and reading English is an advantage

# Project ownership

The selected consultant will work under the supervision of:

- Head of Central Accounting, Lone Læbel Ehlers, lone.ehlers@drc.ngo

# Location and support

Danish Refugee Council headquarters, Borgergade 10, 1300 København K

The Consultant will provide her/his own computer and mobile telephone

# Submission process

Please Refer to the tender dossier

# Evaluation of bids

Please Refer to the tender dossier

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.