DRC

Terms of Reference (TOR)

for

Consultancy: 4Mi Data Collection on Afghan movements to and through Türkiye

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

About the Mixed Migration Centre

The Mixed Migration Centre (MMC) is a leading source for independent and high-quality data, research, analysis and expertise on mixed migration. MMC aims to increase understanding of mixed migration, to positively impact global and regional migration policies, to inform evidence-based protection responses for people on the move and to stimulate forward thinking in public and policy debates on mixed migration. MMC’s overarching focus is on human rights and protection for all people on the move. MMC focuses on 6 regions, with regional teams in each of these: Eastern Africa & Yemen, North Africa, West Africa, Asia, Latin America and the Caribbean, and Europe. Read more about MMC here: www.mixedmigration.org. MMC is part of the Danish Refugee Council (DRC), a leading humanitarian organization responding to displacement and mixed migration in 40 countries.

Since 2014, MMC has been implementing 4Mi as its flagship primary data collection system which is an innovative approach that helps fill knowledge gaps, and inform policy and response regarding the nature of mixed migratory movements and the protection risks for refugees and migrants on the move. 4Mi has a unique network of field enumerators situated along frequently used mixed migration routes and in major migratory hubs. It aims to offer a regular, standardized, quantitative system of collecting primary data on mixed migration. In Asia, 4Mi has been active and implemented in Afghanistan, India, Indonesia, Thailand and Malaysia. Read more about 4Mi here: http://www.mixedmigration.org/4mi/.

# Purpose of the consultancy

The Mixed Migration Centre seeks proposals from a consultant to implement 4Mi data collection in Türkiye for a period of 6 months to collect data on Afghan mixed movements to and through Türkiye in selected locations.

# Background

Türkiye is both a country of transit and destination for people in mixed migration movements acting as a transit corridor for people crossing to Europe from the Middle East, Asia, and Africa, through both the land borders with Greece and Bulgaria and the eastern Mediterranean Sea. Migration along the eastern Mediterranean route peaked in 2015 when more than 850,000 people arrived in Greece after passing through Türkiye, most of them fleeing war in Syria, while others were driven by poverty, persecution and conflict in Afghanistan, Iraq, Pakistan and other Middle Eastern and African countries. Since 2018, Afghan nationals have constituted the largest group of new irregular arrivals.

Currently, Türkiye hosts the world’s largest refugee and migrant population, with numbers close to 4 million. Syrians constitute the largest group at 3.6 million, with 330,000 people from other nationalities also included. Over 98% of refugees and migrants in Türkiye live in urban, peri-urban and rural areas, with the remaining held in Temporary Accommodation Centres.

The Mixed Migration Centre (MMC) aims to document these complex migration dynamics in Türkiye through data collection and research with refugees and migrants, with the aim to increase understanding of who is taking these routes, the drivers of their decision to migrate, the routes they take and the conditions of their journey, including the protection risks they face and their needs. As such, the information will be used to influence global and EU migration policies such as to a certain extent the new pact on migration and asylum.

# Objective of the consultancy

The primary objectives of this consultancy will be:

- Who is undertaking mixed migration journeys? What is their socio-demographic profiles?

- What do refugees’ and migrants’ journeys look like: route, duration, conditions, financing, and assistance?

- What is motivating refugees and migrants to make the journey?

- What dangers do refugees and migrants face on the journey and where (including frontiers to enter the EU)?

- How vulnerable are migrants on their journey, and what determines their vulnerability?

- How prevalent is smuggling and how does it manifest itself?

- How are decisions made regarding migration and the migration journey and what influences those decisions?

The consultant will be required to identify, recruit and supervise 15 field enumerators to conduct 4Mi migrant survey interview with Afghan refugees and migrants in selected locations within Türkiye.

# Scope of work and Methodology

The consultant is expected to use a quantitative data collection method.

Phase 1. Desk review to inform data collection sites

On the basis of a brief desk review to feature in the inception report, the consultant will refine sampling locations and ensure alignment with 4Mi’s global sampling frame. The consultant may propose up to 10 locations, specifying whether they are locations of settlement, transit, and/or points of crossing into Türkiye.

At project kick-off, MMC will share and train the coded 4Mi survey, and data collection SOPs, and guidance as well as existing training documentation.

Phase 2. Data collection

After identifying, in coordination with the MMC team, the specific locations to conduct 4Mi data collection in phase 1, the consultant will recruit 15 Afghan enumerators in each location, organize and administer trainings in coordination with MMC to ensure use of 4Mi training documentation as well as survey SOPs. Pilot surveys shall be built into the workplan per each selected location and sent to MMC for review. The MMC 4Mi regional team will provide the consultant with a Training of Trainers, either in person (in SA) or remotely. The standard 4Mi survey is already coded and translated.

Data collection will take place in selected locations, 1,350 surveys with Afghan refugees and migrants (spread across the selected locations). Data collection should take place face-to-face using a mobile-phone-based application to collect the data, and surveys automatically uploaded to the regional server for the MMC 4Mi regional team to validate and clean data. The consultant will be responsible for ensuring that enumerators have smart phones to conduct 4Mi surveys. The MMC 4Mi team will liaise with the consultant to provide feedback on data quality to enumerators. The consultant will provide day-to-day support and supervision to enumerators throughout data collection.

Phase 3. Report writing

The consultant will draft a final and brief report (5-10 pages) providing an overview of the successes and challenges of data collection on refugees and migrants in Türkiye as well as lesson learned. The report should also provide an overview of the field enumerators observations on dynamics of Afghan movements to and through Türkiye in terms of reported places of transit, organisation/arrangement of journeys, and reported protection risks and incidents.

# Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1 Desk review | Presentation | A brief inception report (2-3 pages) | 2 weeks |
| Phase 2 Data collection | 1,350 surveys | Identifying and recruiting 15 Afghan field enumerators in selected location field visits Collect data (225-240 surveys per month) | 5 months |
| Phase 3 Reporting | Final report | Prepare first draft report (5-10 pages) Feedback from MMC to submit the final report | 2 weeks |

The consultant is responsible for ensuring that the final report is fully copy-edited and complies with MMC’s editorial and style guidelines. MMC shall provide a template for the report.

# Duration, timeline, and payment

Timeline

Activities / steps to feature in workplan:

- Completion of brief inception report, which outlines: an agreed sampling strategy that suits the objectives of 4Mi in Türkiye, based on demographic characteristics in addition to pre-defined MMC sampling criteria (e.g., respondents over the age of 18 who have been in the country for less than two years); the suggested language/s of surveys; proposed survey locations; and any other key methodological features agreed upon by the consultant and MMC.

- Validation of the inception report by MMC and consultant’s integration of any feedback;

- Enumerator recruitment and training. MMC will share existing training documentation, and SOPs on surveying. Trainings can be adapted to the specific context and sampling framework in a country. If errors or inconsistencies are spotted by the MMC team while conducting the cleaning and validation, the consultant is expected to feed this back to enumerators and conduct any relevant re-training;

- 4Mi data collection (1,350 4Mi surveys) in Türkiye;

- Writing of brief report on overview of lessons learned from fieldwork, enumerators observations, as well as Afghan mixed movements to and through Türkiye;

- Full copy-editing of report by consultant before submission to MMC;

- Validation of report and integration of any feedback by MMC;

Total number of working days should not exceed six (6) months for the hired consultant.

Estimated start date of consultancy: July 1, 2023

Estimated end date of consultancy: December 31, 2023

Duration

The total expected duration to complete the assignment will be no more than 6 months.

The consultant shall be prepared to complete the assignment no later than December 31, 2023.

Payment

40% at the validation of the inception report;

60% at the submission of the total number of surveys and final report.

It is anticipated that the consultant will be in regular contact with the primary contact point according to a timetable that will be finalized during the inception phase. The contact point will take responsibility for ensuring timely responses to drafts and inputs to the consultant.

# Proposed Composition of Team

- Project Coordinator

- Project Officer

- 15 Field enumerators

# Eligibility, qualification, and experience required

## Essential:

- The consultancy is open to firms. The research team managers should have an advanced degree (Master or PhD) in migration studies or the social sciences, with expertise in quantitative research methods.

- At least five years of experience conducting primary data collection and managing research projects, with at least three years of these being within the migration field.

- Proven experience in designing and leading research on migration and similar relevant topics.

- A proven knowledge and understanding (e.g. through prior publications or data collection) of mixed migration dynamics in Türkiye.

- Familiarity with the Türkiye context and proven access to relevant stakeholders for data collection permits/authorization in Türkiye.

- Ability to independently carry out data collection in Türkiye and expertise with data collection specifically using a survey tool.

- Familiarity with the MMC 4Mi Methodology.

- Excellent analytical and reporting skills.

- Excellent command of spoken and written English.

## Desirable:

- Previous experience with 4Mi methodology and data

- Previous experience with MMC

- Experience using phones or tablets to collect data

- Türkiye-based consultant, research group, or organization strongly preferred.

# Technical supervision

The selected consultant will work under the supervision of:

- MMC Asia Regional 4Mi Coordinator, Abdullah Mohammadi, abdullah.mohammadi@mixedmigration.org

- MMC Asia Regional Research Officer, Shreya Bhat, shreya.bhat@mixedmigration.org

# Location and support

Istanbul, Ankara, Van, Erzurum, Konya, Kayseri, and Eskisehir.

The Consultant will provide her/his own computer and mobile telephone.

# Travel

>If some travel will be required, please write the purpose of the travel.

Define the condition (e.g.: The Consultant will therefore be expected to arrange transportation, accommodation, insurance, food and to make adequate provision in the Financial Proposal). <

# Submission process

Interested applicants who meet the required experience and qualifications are invited to submit the following documents to: tender.ro04@drc.ngo no later than June 26, 2023, 23:30 CET and specify the subject: Consultancy: MMC 4Mi Data Collection in Afghans in Türkiye.

- Research proposal, highlighting the capacity and experience to independently carry out data collection in Türkiye as well as to implement MMC’s tools and methodological approach as per the ToR and MMC’s website.

- CV including references/links to previous relevant research and data collection exercises, which provide evidence of similar services performed in the past.

- Proposed workplan of activities with timeline and deliverables.

- Breakdown of the budget, which shall cover all costs over the course of the consultancy including A. Consultancy fees – daily and total, B. Data collection/analysis costs, C. Travel costs, D. Miscellaneous. All costs must be inclusive of all applicable taxes.

- If short-listed, you may be asked to provide your certification of registration, certificate/s of completion on comparable projects, and/or any relevant degree confirmation certificates/diplomas.

- Annex A Financial proposal providing the total cost of service fees in USD inclusive of all applicable taxes (Must be on the DRC RFQ Tender file).

- Annex B (DRC general conditions of contract) in attached documents acknowledged and signed.

- Annex D (supplier code of conduct) in the attached documents is acknowledged and signed.

- Annex E (The supplier registration form) completed and signed.

# Evaluation of bids

For the award of this project, MMC/DRC has established evaluation criteria which govern the selection of offers received. The offer will be evaluated using the following criteria, and points will be allocated on a scale from 1-10 for each of the criteria stipulated below, whereas the weighting is as follows:

- 40% - Research proposal, demonstrating the capacity and experience to independently carry out data collection in Türkiye

- 20% - CV including references of previous relevant research and data collection exercises

- 20% - Proposed workplan of activities and deliverables

- 20% - Financial proposal

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.