DRC

Terms of Reference (TOR)

for

Evaluation of Strengthened Collective Protection Analysis Contributing to Humanitarian and Developing Planning and Response Project

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

The Danish Refugee Council - Global Protection Unit, Department for Strategy Programme and Learning (SPL), seeks proposals from a consultant (or team of consultants) to conduct an evaluation of the Strengthened Collective Protection Analysis Contributing to Humanitarian and Developing Planning and Response project.

# Background

In 2021, the GPC endorsed the Protection Analytical Framework (PAF), a structured approach to guide robust, context-specific protection analysis. The endorsement of the PAF responds to a long-standing gap of having an agreed core approach to protection analysis, providing the foundation for informed and evidence-based decision making for strategies to reduce or prevent protection risks in the humanitarian response.

DRC, in collaboration with the Global Protection Cluster, IRC, UNHCR, OCHA, UNDCO and DEEP is implementing a project supported by the Bureau of Humanitarian Affairs (BHA) that aims to strengthen joint protection analysis in five Protection Clusters (Burkina Faso, Ethiopia, Mali, Niger and South Sudan). The project focuses on building the capacity of five Protection Clusters in joint protection analysis using the PAF as the framework to guide the analytical process and structure the information, and DEEP as a tool to support the compilation, organising and structuring of secondary and qualitative data and information.

The project implementation from October 2022 until July 2023, included various components:

- In-person training on protection analysis in each country

- Online coaching and mentoring sessions

- In-person joint analysis workshop

- Production of protection analysis updates (PAUs)

# Objective of the Consultancy

The purpose of the evaluation is to evaluate the performance of the project and build on the lessons learned report produced within the project, to further identify recommendations on joint protection analysis processes. In particular the evaluation will examine the following key activities and outputs:

- The effectiveness and quality of:

  - The in-person trainings;

  - The online coaching and mentoring sessions;

  - The in-person joint analysis workshops;

  - The protection analysis produced including the PAUs;

- Whether protection analysis has been used to inform other processes and/or whether there is an intention to do so, including protection sector strategy and response, HNOs, and CCAs;

- Whether the project has contributed to a more established and documented analysis workflow in the five targeted clusters, through the use of the PAF and DEEP;

- Whether and how the use of DEEP was taken up and contributing factors that led to this uptake;

- Identify best practices, lessons learned, strengths, and challenges in achieving the expected project results.

# Scope of Work and Methodology

The evaluation will examine the strengths and weaknesses of all activities within the project, in addition to the following questions:

- To what extent did the project achieve its overarching goal of strengthening protection analysis that informs humanitarian and development planning and response? What aspect of the project added most value to protection clusters in doing protection analysis?

- To what extent have the project’s interventions adhered to planned implementation and achieved intended goals, purposes and outcomes? What factors promoted or inhibited adherence to plans and targets?

- Was the project successful in producing protection analysis that informs wider humanitarian planning processes? Will the analysis produced through the PAF-DEEP project be used in other analysis/planning processes?

- Was the project successful in engaging different protection cluster actors, including local actors, in doing joint protection analysis?  Are partners who attended any of the processes (trainings, coaching and mentoring or workshop) intent on using these skills in other processes?

- What was the relevance of DEEP in support of protection analysis processes?  How relevant is DEEP for wider use within the protection sector?

- What were the strengths and weaknesses to the trainings, coaching and mentoring sessions, joint analysis workshops, and the analysis produced? What was the most beneficial in these processes and what contributed to success or not?

- Were there any other changes, expected or unexpected, that came about through the PAF-DEEP project?

Mixed methods will be used in the evaluation including key informant interviews and surveys. Project documentation will be used, including:

- Baseline report

- Protection Analysis training questionnaire/feedback

- Online coaching and mentoring questionnaire/feedback

- Joint analysis workshop questionnaire/feedback

- Project lessons learned report

- Other supporting documents will be used to complement evaluation efforts.

This data will be readily available and shared upon the start of evaluation, in order for the data to be analyzed. In order to provide holistic answers to the questions listed above, this information will be supplemented by a survey, to be developed by the consultant(s). The survey is administered to the five protection clusters targeted through the PAF-DEEP project and should consist of the following indicators:

- #/% of respondents who thought the protection analysis processes within the cluster were strengthened through the PAF-DEEP project

- #/% of respondents who intend to use/have used the produced analysis for other analytical/planning processes

- #/% of respondents who thought DEEP is relevant to protection cluster analysis

- #/% of respondents who thought the PAF-DEEP project contributed to wider consultation/engagement of protection cluster partners to analysis processes

This survey can be disseminated to clusters and partners, through using the lists of those who attended training, coaching and mentoring sessions, and the workshop. The survey should be followed up and complemented by key informant interviews, which at a minimum should include:

- Project staff (senior analysts, protection analysis specialist, global protection advisor) (4x)

- GPC colleagues (1x)

- Protection clusters – one interview with each of the five clusters (5x)

- Participants to the workshop (one per country – local NGO partner to get their perspective).

DRC will disseminate evaluation findings with BHA, the five protection clusters targeted throughout the project, the GPC and other actors engaged in the project. The evaluation will complement the lessons learnt and best practices document.

# Deliverables

The consultant is responsible for the satisfactory delivery of all outputs outlined below.

| Phase | Deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1: Inception | Start evaluation | Kick-start meeting and introduction calls | 1 working day |
|  |  | Desk review of existing project materials | 2 working days |
|  | Methodology | Develop methodology and interview questions | 3 working days |
|  | Review by DRC | Review of materials by DRC – allow for up to 2 days. | / |
| Phase 2: Conducting evaluation | Survey | Develop and administer survey | 1 working days |
|  | KIIs | KIIs with all stakeholders | 5 working days |
| Phase 3: Evaluation report | Analysis | Analysis of survey results and KIIs, triangulation of data | 5 working days |
|  | Report drafting | Draft evaluation report | 3 working days |
|  | Finalised report | Incorporate feedback and changes to draft report | 2 working days |
| Total no. of working days |  |  | 22 working days |

The deliverables from this consultancy should be delivered by email and in English.

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 22 working days.

The consultant shall be prepared to complete the assignment no later than 15 September.

| Deliverables | Due Date | Approved by | Payment |
| --- | --- | --- | --- |
| Methodology | 30 July 2024 | DRC | 25% |
| Draft report | 30 August 2024 | DRC | 50% |
| Final report | 15 Sept 2024 | DRC | 25% |

# Proposed Composition of Team

# Applications from individuals or team of consultants will be accepted.

# Eligibility, qualification, and experience required

- Qualification:

  - Master’s degree or equivalent in social sciences, development studies, or another related subject.

Evaluator(s) Profile: The evaluator(s) will have the following competencies

- Specific knowledge of the relevant topic from previous work in relevant research and learning function, e.g. through production of guidance notes in MEAL and/or the research and production of learning material related to humanitarian and displacement work

- Demonstrated knowledge/expertise in MEAL in the humanitarian contexts and programs, including significant experience with international humanitarian and development organizations

- Demonstrated knowledge of results planning and results analysis in this context

- Strong analytical skills and ability to clearly synthesize and present findings, draw practical conclusions, make recommendations

- Excellent writing skills

- Working proficiency in both French and English

# Technical supervision

The selected consultant will work under the supervision of the Global Protection Advisor, Brennan Webert (Brennan.webert@drc.ngo).

# Location and support

This is a home-based consultancy No travel is expected for this consultancy.

# Travel

No.

# Submission process

Refer to the RFP letter of invitation.

# Evaluation of bids

Please refer to the RFP letter invitation.

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.

At the time of the evaluation, there is a high chance that these processes (e.g. HPC for 2025) have not yet commenced and/or are at early stages, which means it may not be possible to measure whether protection analysis has been included, which is why the intention to include it may be more applicable.