Terms of Reference (TOR)

for

Consultancy Services for Communication and Dissemination of project’s activities and results

Project: “Safe and legAl alternatives for Pakistani potEntial migrants and migrants on the Route (SAFER)” funded by AMIF programme of the European Union

# 1.   Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement-affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating into a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included in hosting societies; and works with civil society and responsible authorities to promote the protection of rights and peaceful coexistence.

DRC in Italy works to provide services that range from legal counselling to protection monitoring and inclusion of third-country nationals. The aim is to ensure their full access and understanding of rights and duties in Italy and Europe. The main areas of intervention include social housing and socio-economic integration of third-country nationals, social cohesion, health and protection of vulnerable categories, mainly irregular migrants, asylum seekers and refugees.

# 2.   Purpose of the consultancy

The Danish Refugee Council based in Italy seeks proposals from a consultant to overtake all the tasks that constitute Work Package n. 2 “Communication and dissemination” within the project “Safe and legAl alternatives for Pakistani potEntial migrants on the Route (SAFER)”, funded by the AMIF programme of the European Union.

The purpose of the consultancy is to ensure the visibility of project activities and the involvement of the target groups and the relevant stakeholders, through a comprehensive, multi-media and multi-channel communication strategy. This will have the overall objective of increasing the dissemination of the project’s scope, rationale and results in three partners’ EU Countries (Italy, Greece and Bulgaria) and potentially throughout the European Union.

# 3.   Background

DRC Italy is a beneficiary partner of the EU-funded “SAFER” project, with a duration of 24 months (started on 1st May 2023), of which Fondazione European Research Institute (Italy) is the lead and KMOP (Greece) and University of Sofia (Bulgaria) are other beneficiary partners. The project’s main objective is the design and implementation of an information and awareness campaign for Pakistani nationals on the risks of irregular migrations and the provision of information about legal and safe alternatives highlighting reliable sources and spokespersons.  This campaign will be launched in five regions in Pakistan (Islamabad, Punjab, Khyber Pakhtunkhwa, Baluchistan and Sindh) and will not only directly engage with Pakistani nationals residing in Pakistan, but also with those who are already on the route to Europe and with the diaspora communities in European countries.  For people on the move, project partners will create and implement a platform, also available from smartphones, to provide useful information that could reduce the risk of harm and victimisation by raising awareness on all the relevant landmarks in the country in which they are, such as the Red Cross camps, hospitals, legal clinics, embassies and international organisations location. This action will be accompanied by the establishment of a hotline for potential and actual migrants: the hotline will be available for all the individuals in need of receiving information on a specific subject that could affect them.

The selected Consultant will oversee the creation of adequate dissemination and communication action plan through the partners’ countries (Bulgaria, Greece, Italy) and in the wider EU. The Consultant will help to ensure visibility and support to the project’s activities and results, as well as to increase their reach within and beyond the project’s scope.

# 4.   Objective of the consultancy

The communication agency will overtake all the tasks that constitute Work Package n. 2 “Communication and Dissemination” within the overall project, ensuring the visibility of project activities and the involvement of the target groups and the relevant stakeholders, through a comprehensive, multi-media and multi-channel communication strategy.

The communication strategy will be structured around a storytelling approach and will give great importance to the personal stories of Pakistani nationals who experienced migration and to the risks and dangers they’ve encountered, with the overarching goal of disseminating their stories, raising awareness and increasing protection of current and/or potential migrants.

The overall objectives of the consultancy are:

- Ensure the visibility of project activities and results;

- Ensure the involvement of the target groups and relevant stakeholders;

- Increase the dissemination of project results;

- Give voice to the direct beneficiaries through a podcast series.

# 5.   Scope of work and methodology

The Consultant will be required to prepare a detailed methodology and work plan indicating how the objectives of the Work Package on Communication and Dissemination will be achieved. The content produced will be fully compliant with GDPR and will make sure that names of participants will not be included.

Tasks

- TASK NAME: Design and Implementation of a Dissemination and Communication Plan (DCP).

Task description: A dissemination and communication plan will be developed by the consultant with contributions from all project’s partners. The development of the plan will provide partners with the adequate materials and guidelines to allow spreading of information on project activities and results.

Deliverable 1a
Development of a communication kit comprising of, at least:

- Project’s visual identity and logo creation;

- Website page on existing partners’ websites;

- Communication guidelines for stakeholder engagement;

- Provision of a toolkit to project partners for the elaboration of press releases to generate media coverage;

- PowerPoint presentations templates;

- Guidelines for dissemination of project results (i.e., guidelines on how to organise a dissemination event, how to present the project both in written and oral way to external audience).

Dissemination target: Partners.

Reporting format:

- All the materials produced as part of the communication kit will need to be gathered in a 25-page electronic document.

- Language: English.

Duration: July - August 2023 (2 months).

Deliverable 1b

Project factsheets (tot n. factsheets 4): each factsheet is a 1-page document that will be elaborated and delivered according to project progression and based on inputs from partners.

Dissemination target: general public.

Reporting format:

- 16 electronic documents (1 page each, 1 each language).

- Languages: English, Italian, Greek and Bulgarian.

Duration: each factsheet will be required on the basis of project milestones with due date in October 2023, March 2024, October 2024, March 2025.

Deliverable 1c

Production of 3 press releases to generate media coverage around the project’s activities, events and results.

Dissemination target: general public, relevant stakeholders and press.

Reporting format:

- Max 2-page document (each press release).

- Language: English.

Duration: each press release is linked to project’s milestones with due dates in June 2024, October 2024, and April 2025.

Deliverable 1d

Final policy recommendation paper that will contain project results and policy recommendations (all content will be provided by project partners). Dissemination target: policymakers, academia, Institutions, CSOs, and other relevant stakeholders.

KPI: at least 20 policymakers receive policymaking recommendations.

Reporting format:

- 20-page document (PDF)

- Languages: English, Italian, Greek and Bulgarian.

Duration: November 2024 – March 2025.

Deliverable 1e

Provision of support in the organisation of the communication activities related to the project’s final dissemination event in Bruxelles (elaboration of the agenda, invitations to the meeting, mapping of potential attendees, short interviews with attendees, final press release -cfr. deliverable 1c-).

Dissemination target: project partners, policymakers, academia, Institutions, CSOs, and other relevant stakeholders.

Duration: March-April 2025 (2 months).

- TASK NAME: Development and follow up of a Social Media Plan.

Task Description: The Consultant will oversee the following tasks:

Deliverable 2a

Mapping of the social media currently used by partners (Facebook, Twitter, Instagram, LinkedIn, Youtube, etc.) and creation of 1 dedicated social media project profile on the selected dissemination channel.

Reporting format:

- Excel file + 2 pages-report (PDF)

- Language: English

Duration: due date August 2023.

Deliverable 2b

Social media management and editorial strategy: in collaboration with partners, development of a strategy to ensure effective project’s dissemination that aligns with the overall communication goals, which implies the use of a consistent tone of voice and content.

This includes the creation of an editorial strategy and calendar and drafting of content for the selected partners’ social media channels and for the dedicated social media profile, with inputs from partners. This will include either the creation of ready-to-use content (skills required: graphic design, copywriting, video making and editing), as well as templates to be modified and used autonomously by project partners on their channels.

Dissemination target: general public in the four countries (Italy, Greece, Bulgaria), academia, Institutions, CSOs, and other relevant stakeholders.

KPIs:

- Copy of posts on SoMe (1/month) gathered in a document shared on the project’s Drive folder

- Set-up of a dedicated online space where partners have access to the ready-to-use content and the templates.

Reporting format:

- Document (Word)

- Link and log-in to online platform

Duration:  from July 2023 to May 2025. 1 post/month. Even though the task is supposed to last for the entire duration of the project, it will not require full-time commitment from the consultant.

Deliverable 2c

Report on overall social media performance (number of visitors on the project’s webpages, retention rates, session duration, GDPR-compliant relevant data on users–geography, demographics and gender – followers’ dynamics on the selected social media channel, impressions and engagement, no of posts).

Reporting format:

- 5-page document (PDF)

- Language: English

Duration: due dates March 2024 and March 2025.

- TASK NAME: Production and dissemination of a podcast series.

Task Description: Collection of stories, expert contributions and facts to inform a series of 5 podcast episodes, published on the partners' channels and on at least 1 streaming platform. The podcast series will be structured around a storytelling approach and will give great importance to the personal stories of Pakistani nationals who experienced migration and on risks and dangers they’ve encountered, with the overarching goal of disseminating their stories, raising awareness and increasing protection of current and/or potential migrants.

Deliverable 3a

Podcast series (no. episodes 5; duration/each episode 15 minutes ca; language: English).
The deliverable will include the following milestones:

- Preparation Phase: collection of testimonies and content from partners. Elaboration of a Plan. Duration: May-June 2024 (2 months). Reporting format: document (Word).

- Script writing and production (recording, post-production and editing of 5 episodes+ scouting, selection and upload on streaming platforms). Duration: July 2024-February 2025 (9 months). Reporting format: scripts on a document (Word), recordings.

Deliverable 3b

Dissemination of the 5-episode series. Duration: March-April 2025 (2 months). Reporting format: 3-page report document (PDF).

6.   Deliverables

The Consultant will submit the deliverables listed at point 5 following the timeline below:

The Consultant will provide all the requested documentation by email and using an online document storage (Drive).

# 7.   Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 22 months.

The consultant shall be prepared to start the assignment no later than 01/07/2023.

The budget for the consultancy will include the professional fee, design, production and promotion expenses and supply costs of the agency.

The payments will be made in Euros with the following schedule:

- Twenty percent (20%) will be paid upon completion of preparatory activities, including submission of the deliverables 1a and 2a (September 2023);

- Twenty percent (20%) will be paid in February 2023;

- Twenty percent (20%) will be paid in July 2024;

- Twenty percent (20%) will be paid in December 2024;

- Final twenty percent (20%) will be paid upon completion and submission of deliverables (April 2025).

# 8.   Eligibility, qualification, and experience required

Essential requirements:

- Proven business experience of at least 5 years in producing media content.

- Proven experience in conducting communication campaign for non-profit entities focusing on PR and social networks.

- Technical skills: graphic design, social storytelling and copywriting, photo creation and video making and editing, podcast production, publishing and distribution, familiarity with a variety of social media analytics tools and content publishing platforms.

- Written and spoken fluency in English. Capacity for translation of content into Bulgarian, Greek and Italian (when needed).

- Ability to develop content through a creative and innovative approach and ability to find cost-effective alternative methods of communication and message transmission.

- Excellent project management and organisational skills.

- Flexibility to perform the work at a high-quality level during the contract period and to make changes when requested with attention to detail.

- Ability to work independently, coordinate with different stakeholders and contribute to a teamwork process.

Desirable:

- Experience covering social, humanitarian and development subjects.

- Experience working in international and multicultural teams.

# 10.            Technical supervision

The selected consultant will work under the supervision of:

- DRC Italy Programme Coordinator, Francesca Pisano, francesca.pisano@drc.ngo

# 11.            Location and support

Address of the work assignment: Remote

The selected consultant(s) needs to utilize her/his own equipment and any other resources for performing the task.

# 12.            Submission process and evaluation of bids

Kindly refer to Request for Proposal No.:	 RFP-ITA-000007