DRC

Terms of Reference (TOR)

for

Minimum Economic Recovery Standards (MERS) & CoP Facilitator

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

The Danish Refugee Council is a member of the Global MERS Advisory Committee and a MERS Focal Point organisation (an organisation that has committed to the mainstreaming of the MERS within its programming to improve overall programme quality and outcomes for people of concern).

The MERS are undergoing a period of transition and DRC, as part of a BHA-funded and IRC-led project, is overseeing this process whilst also continuing to maintain support for critical MERS programmes, in close collaboration with other MERS and Markets in Crisis (MiC) Advisory Committee members.

# Background

The Minimum Economic Recovery Standards, or MERS, were first drafted in 2007 with financing from USAID and facilitated through The SEEP Network and its partner relationships working across both the humanitarian and development sectors. The MERS look to improve the uptake and use of quality market-based programming (MBP) and market systems development (MSD) concepts across the crisis lifecycle by outlining key standards in programming in the MERS Handbook. The MERS are cross-sectoral in their application and offer the potential to bridge the language and programming divide between humanitarian and development actors. The MERS, like the Sphere Standards, have been an important resource for field staff both supporting design of and advocating for market systems programming.

The Standards were developed through the joint efforts of more than 90 agencies and over 175 practitioners and are overseen by the MERS Advisory Committee (AC). To date, the MERS have undergone three iterations to maintain their relevance with changing contexts, priorities and programming approaches.

Acknowledging the need for the MERS to go beyond that of just the standards themselves (through the MERS Handbook) to ensure their uptake and use, the MERS programme also includes a history of organisational mainstreaming initiatives (and supporting resources) and influential partnership networks created in different contexts across the world. Practitioners from over 150 organizations have already participated in MERS training and the MERS were the most frequently downloaded resource from the The SEEP Network’s website.

Following the unfortunate collapse of The SEEP Network in late 2021, efforts were undertaken by the MERS and MiC AC members to safeguard these resources to ensure both continued public access and future management of the MERS, particularly in terms of maintaining quality of the Standards and increasing their uptake and use.

Reporting to DRC and the MERS AC, this part-time 9-month consultancy is the result of the efforts to facilitate the transition of the MERS resources and relationships to a long-term custodian, as well as take this as a positive opportunity to revisit the overall MERS strategy and governance approach, to embed learning from recent years to improve the relevance and uptake of the MERS going forward.

The general consensus among MERS AC members is that the MERS should not be hosted in the long term by an implementing organization but rather by one focused on learning or knowledge, which has the benefit of appearing more neutral to members and has a global network of practitioners.

Whilst this host identification process is underway, DRC will take lead in maintaining ongoing MERS activities already committed to prior to the collapse of SEEP as well as working to ensure continued public access to MERS resources through the Humanitarian Standards Partnership.

- Objective of the consultancy

The primary objective of this consultancy will be for the Consultant to act as a facilitator responsible for identifying the future host of the MERS who will be responsible for maintaining the relevance of and mainstreaming the MERS amongst the humanitarian, development and donor community by:

- Facilitating a neutral and robust due diligence process to assist the MERS AC (inclusive of DRC) in identifying and selecting a long-term host for the MERS; and

- Acting as the facilitator between the MERS AC and selected long-term host to build consensus on an appropriate governance structure and future MERS strategy and its financing.

The secondary objective of this consultancy will be to provide administrative support to DRC (in its capacity as a MERS Advisory Committee member) to facilitate ongoing activities with MERS Focal Point organisations (these are organisations who were committed to promoting and mainstreaming the MERS within their organisations and were supported with training and mentorship from specialists via The SEEP Network) whose continued engagement will ultimately inform the future MERS strategy requirements.

# Scope of work and Methodology

The Consultant will coordinate the following activity streams to deliver the objectives of this consultancy. The activities will run concurrently, rather than sequentially, with the Consultant working with DRC to identify the most appropriate workplan to achieve the activity objectives across the project timeline.

Activity 1 – Develop and coordinate a transparent due diligence process to identify and shortlist potential host candidates

Whilst an online host is poised to take on stewardship of the MERS copyright, their involvement is limited to maintaining the copyright and web-based resources of the MERS handbook only. All other public and internal MERS assets will need to be transferred to a new host as well as management of the MERS project and original MERS Handbook content.

The MERS project will need a host organisation to take responsibility of managing, maintaining and updating the MERS content and supporting mainstreaming, dissemination and learning activities. The potential host organisation does not necessarily need to be a MERS or Humanitarian Standard Partnership (HSP) expert.

The proposed tasks within this activity are as follows and are expected to be conducted in consultation with the MERS AC and in close alignment with the MiC Facilitator:

- Develop and coordinate a transparent due diligence process for selecting a new knowledge management and learning organisation/platform to host the MERS project with particular focus on:

  - Develop process for candidate identification and shortlisting (minimum of three)

  - Develop the selection criteria – functional, technical, strategic, cultural, financial

  - Identify further information candidates will require to inform their proposals

  - Facilitate creation of proposal workshops wherein candidates will propose their ambitions on hosting, promoting, maintaining and mainstreaming the MERS as well as the opportunities for financing these activities going forward

  - Facilitate selection of host organisation with MERS, MiC AC, IRC and BHA

Activity 2 – Understanding the future of MERS

Concurrently with Activity 1, the Consultant will work with DRC and the MERS AC to create a list of basic requirements and opportunities for the future of the MERS based on their collective experience to date.

This work will summarise mainstreaming learning from previous MERS programmes to inform the foundations/starting points of a host organisation’s future MERS strategy, to increase awareness and mainstreaming of their use, with particular focus on content relevance and promotional activities informed by:

  - MERS uptake successes and challenges to inform any future MERS content revisions and, where relevant, financing opportunities;

  - Identifying appropriate scaling and sustainability opportunities. These include: organizational mainstreaming activities through the MERS Focal Point scheme; cluster outreach strategies to widen reach and embedding into practices particularly in WASH, Shelter and Nutrition, building on previous MERS projects expanding into new sectors; outreach to market systems development actors to identify opportunities across the nexus; and investigation of the potential for MERS unlocking humanitarian and resilience investing;

  - Applying MERS to non-livelihood sectors through sector specific learning and/or cluster outreach strategies; and

  - The case for integrating inclusion topics (gender, disability, social capital, protection, environment/ climate change, finance) into the MERS narrative.

Ideally, host candidates presenting their proposals in Activity 1 will be able to articulate their strategic vision for the MERS, building on the future vision articulated by the MERS AC.

Activity 3 – Co-creation and agreement of MERS strategy, governance and funding approach selected host

Once the preferred host is selected, the Consultant will be expected to establish a way of working with the host organisation to ensure the co-creation of:

- Future of MERS strategy;

- Governance model and funding strategy to deliver the MERS strategy with preferred host;

- Online outreach/marketing strategy for MERS; and

- Hosting agreement

The Consultant will not be expected to create all the content - this would be primarily the role of the host organisation. The Consultant is expected to facilitate the content creation to ensure all views are considered in it by acting as a facilitator/mediator between the host organisation and MERS AC and MiC Facilitator / BHA and that the content is delivered within a given timeframe. The Consultant’s role will need to be explained through the host organisation selection process such that this is seen as a way to support, not hinder, the transition.

Activity Area 4 – Interim Support to Ongoing MERS Activities

The Consultant will provide basic logistical/admin support for ad-hoc virtual meetings with MERS Focal Point Organisations (maximum of two during the consultancy).

# Deliverables

The Consultant will be provided with 30 days over a 9-month period in order to complete the listed deliverables below. The Consultant will provide the work in close collaboration with DRC, MERS AC and hosting partners and determine the best formats for deliverables by activity for the different audiences.

| Activity | Proposed deliverable output & estimated deadline | LOE |
| --- | --- | --- |
| 1 | - Creation and presentation of due diligence process to MERS AC – 15th March - x3 host organisations identified – April - x3 host candidate workshops organised and delivered to MERS AC – mid May - Preferred host selected – End of May – mid-June | 10 days |
| 2 | - Creation of MERS AC point of view on the “Future of MERS” – prior to May workshops | 5 days |
| 3 | - Co-created MERS strategy 2023 – 2027 (in word format) - 31st August - Co-created governance approach (in word format) - 15th September - Co-created financing strategy incl. mapping and opportunity identification (in word format) and online outreach strategy - 15th October - Presentation and agreement of outputs to MERS & MiC AC – 1st November - Final hosting agreement drafted (in word format) - 20th November | 12 days |
| 4 | - Focal Point mainstreaming support seminar (virtual meeting) - date Q2 - MERS global learning event (public webinar on Focal Point learning) - date Q3 | 3 days |

# Duration, timeline, and payment

The total expected duration to complete the assignment will be preferably within a 9-month timeline.

The consultancy will begin by the 1st March 2023. The consultant shall be prepared to complete the assignment no later than 20th November 2023.

The total LOE for the project is 30 days which can be distributed to meet the needs of the activities.

As each activity will be dependent on externalities and inputs from supporting players the proposed deadlines are indicative for discussion. The activity streams will be able to be run concurrently, rather than sequentially, with the Consultant working with DRC to identify the most appropriate workplan to achieve the activity objectives across the project timeline.

The Consultant shall provide an activity cost plan in line with the deliverable requirements and within 30 days LOE (there will be no leeway for time extensions).

DRC is willing to pay up to maximum $800 per day.

# Eligibility, qualification, and experience required

## Essential:

- Project management and coordination skills

- Strategy development

- Ability to facilitate discussion with diverse sets of actors with differing perspectives to build consensus and agreement

- Ability to discuss the relevance of the MERS in driving the uptake and use of MBP across different contexts

- Confidence in facilitating groups and co-design workshops

## Desirable:

- Demonstratable understanding of relevant humanitarian (HSP, Sphere, CHS) and/or development standards (DCED etc) and their importance to program quality, donors and the challenges of integrating them into program activities

- Demonstratable use of the MBP and/or MERS in previous work

- A good understanding of the MERS from a strategic rather than technical perspective

- A good understanding of market systems approaches and their application to the humanitarian and development sector

- An ability to understand the organisational challenges and needs for uptake of the MERS

- Previous experience in coordination / management of knowledge management platforms or Communities of Practice or project with learning / knowledge management as a core component

- Demonstratable engagement with the wider MiC Community of Practice

- Qualification:

  - Educated to degree level in relevant subject (or with at least 7 years demonstratable work-related experience in the humanitarian and/or development sector with work in the field)

- Experience:

  - A minimum of 7 years working in the humanitarian and/or development sector (preferably a mixture of the two) and/or developing knowledge sharing and learning partnerships/collaborations

  - Experience in livelihoods and/or market systems approaches (in any sector), preferably in crisis preparedness, response or recovery contexts will be an advantage

- Language requirements:

  - Written and spoken fluency in English

  - Working knowledge of additional languages e.g. Arabic, French or Spanish is an advantage

# Technical supervision

The selected consultant will directly work under the supervision of:

- Katie Whitehouse (Global Inclusive Markets Advisor, Danish Refugee Council & MERS Trainer)

The selected consultant will coordinate regularly with the:

- MERS Advisory Committee

# Location and support

This assignment will be conducted remotely. No travel envisioned for this project.

The Consultant will provide her/his own computer and mobile telephone.

# Submission process

Interested consultants are expected to submit offers in response to these terms of reference as per the below required technical documents and in line with the requirements as stated in the tender dossier.

Technical Bid:

- Updated CV (maximum 3 pages)

- Proofs of previous similar consultancy conducted by the applicant and/or demonstrated experience conducting similar work. Please note clearly if you have worked with DRC in the past (when, for what service, where).

- A short technical proposal (max. 4 pages) outlining the consultant’s plan for the consultancy based on these ToRs, clearly outlining the proposed methodology for each component.

- Signed financial offer that clearly includes the Consulting Fees unit price per day in USD. If VAT is to be applied, please include in the final bid cost.

# Evaluation of bids

For the award of this contract, the evaluation criteria below will govern the selection of offers received.

The evaluation is made on a technical and financial basis. The proposed offers by bidders will be evaluated using the following criteria, and points will be allocated on a scale from 1 (poor) to 10 (excellent) for each of the criteria below, according to the following weighting:

| 1. Candidate qualifications (Documented by the filled-in Supplier Registration Form, CV, and proof of relevant experience) | - General liability/capacity of the candidate (including support services) - Previous relevant experience (and ability to network/source wider experience) 60% |
| --- | --- |
| 2. Proposed services (Documented by the technical proposal) | - Content of the proposal is suitable for the stated requirements within the proposed timeframes and budget - Quality and depth of consideration of the proposed methodolog(ies) for delivering proposal activities - Access/network with relevant professional networks / organisations likely to engage with activities in proposal 40% |
| Total | 100% |

The best scoring candidates will be invited to an interview to assess the candidates’

qualifications and proposed services. The interviewees will be further evaluated against:

- Previous relevant projects executed

- Quality and feasibility of the proposed methodology

- Professional competencies & experience of the person(s) who will work on the project