DRC

Terms of Reference (TOR)

for

Data collection services in Greece for the 4Mi data collection initiative on mixed migration dynamics (MMC)

# Who is the Danish Refugee Council?

The Danish Refugee Council

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

The Mixed Migration Centre

Part of DRC, the Mixed Migration Centre (MMC) is a leading source for independent and high-quality data, research, analysis and expertise on mixed migration. The MMC aims to increase understanding of mixed migration, to positively impact global and regional migration policies, to inform evidence-based protection responses for people on the move and to stimulate forward thinking in public and policy debates on mixed migration. The MMC's overarching focus is on human rights and protection for all people on the move. The three overall objectives of the MMC are:

- To contribute to a better, more nuanced and balanced understanding of mixed migration (knowledge)

- To contribute to evidence-based and better-informed migration policies and debates (policy)

- To contribute to effective evidence-based protection responses for people on the move (programming)

MMC is a global network, with regional hubs in Africa, Asia, Europe and Latin America hosted in DRC regional offices, and a small central team in Geneva. MMC is part of, and governed by, DRC. While its institutional link to DRC ensures MMC's work is grounded in operational reality, it acts as an independent source of data, research, analysis and policy development on mixed migration for policy makers, practitioners, journalists, and the broader humanitarian sector. The position of MMC does not necessarily reflect the position of DRC. For more information on MMC visit our website here: www.mixedmigration.org

# Purpose of the consultancy

The Danish Refugee Council based in Geneva seeks proposals from consultants to conduct quantitative data collection (survey administration) in Greece.

# Background

The 4Mi data collection initiative

4Mi is one of MMC’s flagship project. 4Mi collects data through in-depth structured interviews, focusing on protection risks and the conditions and experiences faced by people on the move, as well as their motivation for migration. 4Mi fills information gaps around protection and vulnerabilities with a view to informing policy and humanitarian programmatic response as well as enhancing sector understanding and knowledge on migration dynamics.

Regional context

In Europe, MMC has carried out 4Mi data collection in Greece since 2019, and has since engaged in a number of other research initiatives and projects in Europe, all available here. In addition, MMC is committed to respond to changing dynamics and pressing needs for evidence-based programming and policy development in the region.

# Objective of the consultancy

The purpose of this consultancy is to conduct quantitative data collection (survey administration) in Greece. The consultant will be required to conduct and deliver 600 surveys as per MMC’s methodology and research objectives, in close cooperation with the MMC team.

Research objectives

MMC will engage in a new data collection project in Greece, in order to provide evidence-based and up-to-date quantitative analysis on ongoing mixed migration trends and dynamics into Europe.

Quantitative survey will serve to identify quantitative (yet non-representative) tendencies among the target population, using the 4Mi core survey developed by MMC. The questionnaire will cover the following topics:

- Profile: age, nationality, religion, sex, socio-economic status, etc.

- Route and journey conditions: country of departure, transit countries, number of people travelling together, etc.

- Drivers, aspirations and destination intentions: reasons for leaving, decision-making, determination to reach destination, etc.

- Protection risks: perceived risks and dangerous locations, perpetrators, etc.

- Assistance: type of assistance needed, assistance providers, locations where assistance is most needed, etc.

- Smugglers: services provided by smugglers, contacts with smugglers, payment arrangements, refugees’ and migrants’ perceptions of smugglers, etc.

- Financing the journey: sums paid, access to money while travelling, bribes paid, etc.

- Access to information: sources of information used before and during the journey, phone and internet access, social media use, etc.

Additionally, a set of questions (decision making module) will be added to the 4Mi core migrant survey, to further understand the factors that influence the migration-related decision making for refugees and migrants entering Europe through the Eastern Mediterranean route and their intentions for onward movement further into Europe.

Target population

Potential survey respondents will be approached by enumerators based on the following criteria:

- 18+ years old.

- Refugees and migrants both in regular and irregular status.

- Arrived in Greece since a maximum period of two years.

MMC is expecting the sample to respect gender balance.

Locations for data collection and nationalities

Locations for data collection and nationalities will be agreed during the inception phase of the project, following discussion between the selected contractor and MMC

Data collection modalities

Surveys are planned to be conducted face-to-face through electronic data collection (text-based survey solution on phones/tablets). Enumerators shall have a good command of English to receive the training in this language.

# Scope of work and Methodology

Specifically, the consultant is expected to:

- Recruit, contract and supervise a network of enumerators in line with the MMC’s SOPs;

- Organize a training for enumerators (that will be facilitated by MMC), providing an adequate room for this;

- Collect 600 surveys in electronic format (ODK), according to the workplan agreed upon in advance with MMC;

- Cover potential phone credit and transportation prices for the enumerators;

- Provide phones or tablet (hardware) to the enumerators for electronic data collection;

- Identify respondents;

- Ensure that the methodological guidelines shared by MMC are applied for the survey;

- Designate a focal point and set up regular reporting and discussion with MMC, especially during the data collection phase to ensure efficient data collection and high-quality standards.

MMC will provide:

- Methodology and research tools for quantitative data collection, in English, already coded in ODK format. The potential provision of the questionnaire in other languages will be discussed later on with the consultant;

- Training for enumerators on relevant concepts, methodology, the questionnaire, principles and ethics of research in the field, and the Code of Conduct;

- The backend infrastructure (server, ONA administration) for electronic data collection on the phones provided by the consultant.

General requirements:

- The consultant is responsible for all aspects of data security and data protection for the duration of the contract.

- The consultant is responsible for frequently reporting to MMC on progress and any issues regarding deliverables, the timeline, and data quality. When designating a focal point for this project, the consultant should ensure that the focal point has direct supervision over the enumerators in order to secure a direct line of communication and reactivity between both parties.

- The consultant is responsible for adhering to ethical guidelines detailed in the research protocol.

- The consultant is responsible for providing insurance and ensuring compliance regarding human resources.

- The consultant shall adhere to the suppliers Code of Conduct.

# Deliverables

The Consultant will submit the following deliverables:

| Phase | Expected deliverables | Indicative description tasks |
| --- | --- | --- |
| Phase 1 Inception | Inception report | An inception report detailing modalities for carrying out the tasks including: composition of the team, suggested coordination mechanism between the implementing partner and MMC, and all the other elements needed for an effective implementation of the activities and proper coordination with MMC. |
| Phase 2 Pilot | Data collection field pilot report | Test of the survey followed by a short report on the field pilot for potential methodological/technical adjustments to be discussed with MMC before data collection. |
| Phase 3 Quantitative data collection | Survey dataset | Collection of 600 high-quality quantitative interviews in the agreed locations, in electronic format. Surveys are expected to be collected from the beginning of the data collection period and consistently throughout it, with a weekly quota to be established. |
| Phase 4 Wrap up | All data collection documentation | Full documentation regarding data collection, including notes and observations on any changes or modifications. |

To carry out the above-mentioned deliverables, it is expected that the applicant will identify the following positions within the team:

  - Project manager, responsible for the overall implementation of the project and coordination with MMC.

  - Field coordinator(s), responsible for the supervision of the enumerators team(s) and for ensuring that data collection proceeds successfully. The number of field coordinators is to be proposed by the consultant, also depending on whether the proposal is single- or multi-country.

  - Enumerators, directly responsible for collecting the surveys. Ideally, enumerators team should ensure at least one female enumerator per data collection site.

The consultant will provide the documentation by email in Excel format (database of quantitative surveys) and Word format (field pilot report, final notes and observations).

# Duration, timeline, and payment

| Activities | Period envisaged |
| --- | --- |
| Contractualization of the data collection consultant | April-May 2024 |
| Definition of methodological & operational details (data collection sites, respondent recruitment criteria, etc.) (jointly between MMC and consultant) | May 2024 |
| Trainings of enumerators (organised by consultant, content provided by MMC) | May 2024 |
| Field pilot (5 days) | Beginning of June 2024 |
| Data collection of 600 surveys. Surveys are expected to be collected from the beginning of the data collection period and consistently throughout it, with an average weekly quota to be established | June to mid-December 2024 |
| Validation and cleaning of quantitative data | Weekly |

Estimated start date of consultancy: 20th May 2024

Payment for the consultancy will be made as follows:

- 20% upon signature of the contract;

- 25% upon submission of the inception report;

- 25% upon satisfactory receipt of the first 300 surveys;

- 30% upon receipt of the remaining 300 surveys and final data collection documentation.

Date of submission of the finalized dataset and final report: 15th December 2024

MMC estimates that the above activities will require approximately 100 days of work over the indicated period.

# Eligibility, qualification, and experience required

- Research organizations, universities, think-tanks, NGOs, CSOs, or consultancy companies with extensive track record in conducting surveys in Greece;

- Legal and operational ability to independently carry out data collection in Greece and expertise with data collection specifically using an electronic survey tool and respecting the highest research standards;

- Proven expertise in researching / implementing projects on migration, human rights, and/or social justice;

- A proven experience in engaging with migrants;

- Languages: English is essential, other relevant languages would be a plus;

- The selected organization will have to sign and comply with DRC’s Code of Conduct.

# Technical supervision

The assessment shall be completed in close cooperation with MMC Europe. The selected consultant will work under the supervision of Giulia Bruschi, Data and Research Project Manager, MMC Europe,  email address: giulia.bruschi@mixedmigration.org.

# Location and support

The assignment will take place in Greece. All interviews are to be conducted face-to-face.

The Consultant will be expected to arrange transportation, accommodation (when relevant, for instance for the initial enumerators training), adequate equipment (including data collection devices such as tablets or phones), phone credit, and insurance for its team, and to make adequate provision in the Financial Proposal.

# Travel

No travel besides commute in the areas of research is expected for this consultancy. In case the consultant expects team members to come from abroad, it is responsible for all logistical, administrative and financial arrangements, and make adequate provision in the Financial proposal.

# Submission process

Please see Request for Proposal (RFP) section III, clause A.

Candidates should submit an application including:

- Documents requested in the Request for Proposal (RFP), section III, clause A

- Cover Letter

- CVs of the Project Manager, and Field Coordinator(s), including references of previous relevant works (max. 4 pages)

- Technical proposal (max 10 pages) including: proposed approach and workplan, proposed profiles for the team (team leader, enumerators…)

- Financial proposal: budget (in CHF), which shall cover all costs over the course of the consultancy. The budget should be broken down as described below:

A. Consultancy fees – daily and total

B. Technical costs – phones, etc.

C. Travel costs, if applicable

D. Miscellaneous (e.g. insurance, printing, etc. – please specify in the financial proposal)

# Evaluation of bids

The evaluation process consists of three stages: 1) Administrative, 2) Technical and 3) Financial. This process is explained in the Request for Proposal (RFP), section III.

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.

# Terms and Conditions

- The consultant(s) will report directly to Giulia Bruschi, Data and research Project Manager, with regular updates and sharing of partial data and feedback and observations at intervals before the final deadlines for deliverables. They are also likely to interact with other MMC Europe staff, and partners to the project.

- All information presented, obtained and produced is to be treated as the client’s property and is considered as confidential for all purposes other than what is outlined in these ToR. Upon signing the consultancy contract, the selected consultant will be required to sign a confidentiality agreement. The material prepared by the consultant cannot be sold, used or reproduced in any manner (partially or in full) by the consultant without prior permission from PRIME consortium.