Terms of Reference (TOR)

for

Innovation Support Consultancy Services

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates for rights and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Background

The DRC Program Innovation and Business Engagement Unit is responsible for supporting innovation across DRC’s program portfolio. It does so through flexible funding, learning and knowledge management and, to a lesser extent, currently, technical support and advisory on innovation approaches and methodology. DRC currently has over 20 active innovation projects, funded by its internal innovation fund, as well as a range of other innovation initiatives, funded and implemented outside of its central innovation fund. These initiatives primarily focus on the test/pilot/proof of concept stages, usually range from 6 – 12 months in duration, have relatively limited budgets and are usually implemented by existing staff in DRC country offices.

In 2023 DRC conducted a learning review of its internal innovation support services. On the basis of this review, a number of recommendations were made. In particular these relate to strengthening the service offer from the Program Innovation and Business Engagement Unit to the wider organisation in terms of a) technical advisory on the design and scoping of innovation projects, using innovation design and management approaches to strengthen the foundation for successful innovation initiatives, and b) advisory, strategy and methodology support to transition ongoing, successful pilot initiatives to scale.

# Purpose of the consultancy

The purpose of this consultancy is to assist DRC in addressing the recommendations from the DRC Program Innovation learning review, to enhance the service offer from the Program Innovation and Business Engagement Unit to the organisation primarily in terms of:

- Innovation project design support and scoping, strengthening the ability of country offices and global technical leads to scope and design projects with an innovation focus

- Advisory and methodologies to help successful initiatives transition to scale

# Geographical focus, duration & outputs

- Global in scope, covering all of DRC’s geographies, but services delivered virtually, with a preference for in person kick-off and debrief with the core innovation team in HQ Copenhagen

- Duration: services are to be delivered between February – June 2023, with the main period of delivery in March and April, start up in February and wind-down in May/June.

- Outputs are defined below under Scope of Work

- Scope of work

The specific outputs we are looking for are:

- A detailed plan for the consultancy based on these ToR and kick-off meetings with the core innovation team and consultations with 4 – 5 stakeholders in DRC.

- Design and implementation of 1-2 virtual workshops (1 or multiple sessions) with an estimated 15 - 20 participants (DRC is responsible for identifying and inviting participants), focused on ‘design, scoping and planning of an innovation initiative/project’, that will enable participants, based on training, templates and guidance, to qualify ideas into the design of an innovation project plan

- Design and implementation of 1-2 virtual workshops (1 or multiple sessions) with an estimated 15 - 20 participants (DRC is responsible for identifying and inviting participants), focused on ‘transition to scale of successful innovation pilot projects’, that will enable participants, based on training, templates and guidance, to assess the scaling potential of their innovation initiatives and develop a scale or replication strategy for their initiative

- 1 or 2 workshops with the core program innovation team (5 – 8 participants) conducted as ‘training-of-trainers’ sessions, enabling the core innovation team to deliver the workshops and guidance developed and tested under outputs 2 and 3 after the end of the consultancy services

- 30 hours of mentoring and coaching to the innovation team on innovation methodology and strategy and/or direct advisory to existing DRC innovation initiatives on strategy and design, throughout the consultancy duration, to be planned in detail during the kick-off phase.

# Deliverables & Timeline

The Consultant will submit the deliverables as per the indicative timeframe below:

| Deadline | Expected deliverables | Indicative description of tasks |
| --- | --- | --- |
| February 15 | Project kick-off workshop | Based on ToR, the consultant’s proposal and a kick-off planning meeting with the core team, some stakeholder consultations, delivery of a project kick-off workshop (virtual or in person in HQ Copenhagen), setting the scene for the consultancy, clarifying roles and responsibilities between the consultant and the core team and agreeing on timelines |
| 1 March | Design proposal for the 2 workshop categories (outputs 2 and 3) | The consultant’s proposal for workshops under outputs 2 – 3 |
| 15 March – 30 April | Workshop delivery | Delivery of the workshops under outputs 2 and 3, designed and planned under the deliverable above, with a preference for scheduling and implementation in March and April, with room to extend into May |
| 1 April – 30 May | Training-of-trainers workshops | Delivery of one or more ‘training-of-trainers’ workshops as per output 4 |
| 1 March – 30 May | Coaching and advisory delivery to core team and projects | The consultant is requested to present with the proposal ideas for how these advisory/mentoring services could be implemented. They will then be further detailed in the inception phase |
| 30 June | Final learning report with recommendations for DRC | A final, brief learning report (estimated 10 pages) with key reflections from the workshops, mentoring and advisory and recommendations for DRC to further strengthen its innovation function going forward |

# Duration and payment

The total duration is five months, from 1 February, 2024, to 30 June, 2024

The consultant may work from his/her home base, but will be requested to conduct as a minimum the kick-off workshop and training-of-trainers workshops with the core team in HQ Copenhagen.

# Eligibility, qualification, and experience required

For this consultancy DRC is seeking the services of individual consultants or a small team of consultants with the following qualifications:

Required

- Experience in facilitating innovation workshops with humanitarian, development or social sector staff and projects, ideally, but not necessarily focused on design and scale of innovation initiatives, similar to the scope for this assignment

- Ability to design and implement interactive, participatory and motivational online workshops (using teams, zoo, hopin or other well known virtual platforms) with people from various background and various levels of knowledge on innovation methodology

- Knowledge of industry standards in non-profit innovation, and ability to draw on these in the design and implementation of these services

- Experience in coaching/mentoring innovation teams on both strategy and implementation

# Technical supervision

The selected consultant will work under the supervision of the Head of Program Innovation and Business Engagement, Morten Högnesen, morten.hoegnesen@drc.ngo and with day-to-day coordination with the Innovation and Partnerships Specialist, Daniel Higgins, daniel.higgins@drc.ngo.

For additional information regarding these terms of reference or submission instructions, please send your questions to Morten and Daniel at the addresses above.

# Location and support

The consultant may be home based with in-person participation in workshops in Copenhagen as per scope of work

# Submission process

Interested consultants are expected to submit the following items in response to these terms of reference:

Technical Bid:

- Updated CV of key staff (maximum 3 pages)

- 1 sample of previous work (this could be a report, workshop design or another document or product produced by the consultant, evidencing quality of work relevant for this assignment)

- A technical proposal (5 pages maximum) describing how the consultant plans to produce the stated deliverables within the timeframe. Candidates may use their own format.

- A financial proposal which reflects the technical offer and includes an all-inclusive consulting fee covering the proposed number of working days/hours and other expenses (incl. travel for the kick-off and debrief in HQ Copenhagen) Please use the DRC format (annex A2) provided and list the price in DKK.

Please refer to the Invitation Letter for the completer process

# Evaluation of bids

Please refer to the Invitation Letter