DRC

Terms of Reference (ToR)

for

Consultancy: Qualitative Data Collection on mixed migration movements to and through Pakistan

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in nearly 30 countries with 6,000 employees and supported by 6,000 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement-affected people and communities. DRC works during displacement at all stages: In the acute crisis, in exile, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included in hosting societies; and works with civil society and responsible authorities to promote the protection of rights and peaceful coexistence.

About the Mixed Migration Centre

The Mixed Migration Centre (MMC) is a knowledge centre engaged in data collection, research, analysis, policy and programming on mixed migration. MMC has regional hubs in Africa, Asia, Europe and Latin America, with a global team headquartered in Geneva and based in several countries worldwide. MMC aims to increase understanding of mixed migration, to positively impact global and regional migration policies, to inform evidence-based mixed migration responses for people on the move and to stimulate forward thinking in public and policy debates on mixed migration. MMC’s overarching focus is on human rights and protection for all people on the move. The three overall objectives of the MMC are:

- To contribute to a better, more nuanced and balanced understanding of mixed migration (knowledge)

- To contribute to evidence-based and better-informed migration policies and debates (policy)

- To contribute to effective evidence-based protection responses for people on the move (programming)

MMC is part of the Danish Refugee Council. While its institutional link to DRC ensures MMC’s work is grounded in operational reality, it acts as an independent source of data, research, analysis and policy development on mixed migration for policy makers, practitioners, journalists, and the broader humanitarian sector. The position of MMC does not necessarily reflect the position of DRC and vice versa.

MMC's research on mixed migration combines quantitative and qualitative methods to generate evidence on the drivers, experiences, vulnerabilities, and aspirations of refugees and migrants on the move. While 4Mi is MMC's flagship global mixed migration data collection system, providing the world's largest globally comparable primary dataset based on direct interviews with refugees and migrants, MMC also regularly undertakes qualitative research to provide deeper insights into migration dynamics and lived experiences. Through methods such as key informant interviews (KIIs), focus group discussions (FGDs), and in-depth interviews, MMC complements quantitative findings with contextual analysis that informs humanitarian programming, policy discussions, and advocacy. In 2025, MMC Asia and the Pacific has conducted research across multiple countries, including Türkiye, Afghanistan, Pakistan, Indonesia, Thailand, and Malaysia, adapting its methodologies to respond to evolving migration trends and emerging information needs.

For more information on MMC visit our website: https://mixedmigration.org/

# Purpose of the consultancy

MMC seeks proposals from a consultant to implement qualitative data collection in Pakistan for a period of 1 month. The aim is to collect data on mixed movements through i) 5 Focus-group discussions (FGDs) with Afghan migrants and refugees, who were in Iran or who transited through Iran, before arriving to Pakistan and ii) 20 key informant interviews (KIIs) with stakeholders on their perspectives on migration drivers, dynamics and lived realities underlying Afghan mobility from Iran to Pakistan.

# Background

Pakistan has hosted large migrant populations for over four decades. Since the Taliban takeover in August 2021, Pakistan has played an increasingly critical role for Afghans seeking safety, access to consular services for third-country visas, or participation in relocation programmes, serving as both a destination and a key transit country. In recent years, increasing numbers of Afghans have been in Iran or transited through Iran, where many have experienced displacement, precarious legal status, limited access to services, and protection risks before continuing their journeys. Pakistan serves as an important location for engaging with Afghans who have recently travelled through Iran, providing an opportunity to better understand their experiences, decision-making, protection risks, coping strategies, and future intentions. Generating qualitative evidence on these mixed migration experiences will help inform humanitarian programming, policy discussions, and advocacy aimed at improving protection and assistance for Afghan refugees and migrants along the route.

MMC aims to document the migration experiences of Afghan refugees and migrants who have transited through Iran before arriving in Pakistan through qualitative data collection. The study seeks to enrich and triangulate quantitative findings by providing deeper contextual understanding of Afghan mobility from Iran to Pakistan.

# Objectives of the consultancy

The primary objectives of this consultancy will be to understand:

- What are the main drivers influencing Afghan migrants' and refugees' decisions to move from Iran to Pakistan, and how have these been affected by recent developments in Iran?

- What migration routes and border-crossing mechanisms are used by Afghans travelling from Iran to Pakistan, and what factors shape their mobility patterns?

- How do legal status, documentation, and policy frameworks in Iran and Pakistan influence migration experiences, access to services, and protection outcomes?

- What protection risks and challenges do Afghan migrants and refugees face before departure, during transit, at the border, and after arrival in Pakistan?

- How do migration experiences, vulnerabilities, and needs differ across demographic groups, including women, youth, caregivers, and undocumented Afghans?

- What are the immediate assistance, protection, and service needs of Afghans arriving from Iran, and what barriers do they encounter in accessing support?

- How do government institutions, humanitarian actors, and other stakeholders respond to the needs of Afghans arriving from Iran, and how effective are existing coordination mechanisms?

- What are the future intentions of Afghans who have moved from Iran to Pakistan, and what factors influence their decisions to stay, return, or move onward?

# Scope of work and Methodology

The consultant is expected to use qualitative data collection methods to gather insights into the migration experiences, protection risks, and assistance needs of Afghan migrants and refugees who came from Iran to Pakistan.

Phase 1. Desk review to inform data collection sites

On the basis of a brief desk review, which will feature in the inception report, the consultant will:

- Refine sampling distribution and locations to ensure alignment with the sampling frame and the objectives of the study. Participants will be selected using purposive sampling based on the study's inclusion criteria. Snowball sampling may be used, where appropriate, to identify additional eligible participants and key informants through referrals, particularly among hard-to-reach populations.

- Propose up to 3 locations (with a focus on key areas close to borders with Iran and Afghanistan), specifying whether they are settlement areas, transit points, or crossing locations into Pakistan.

- Identify a list of diverse key informants from international/national organizations and government officials.

- Submit an inception report outlining the proposed methodology, detailed work plan, data collection approach, deliverables, and timelines for completing the assignment.

Phase 2. Data collection

In this phase, the consultant will oversee translation of the training materials and qualitative tools, training of enumerators as well as implementation of data collection, ensuring the collection of high-quality, ethically sound data.

For the enumerator training and piloting:

- Translate the training materials and the qualitative surveys into Dari, Pashto and Urdu.

- With support from MMC, the consultant will facilitate training for enumerators, ensuring the use of MMC training materials, survey SOPs and research ethics guidelines.

- Pilot surveys will be conducted and shared with MMC for review before full-scale data collection begins.

Focus-Group Discussions

Data collection will take place face-to-face on paper or using Microsoft Excel or Word. If all participants consent, the FGD may be audio-recorded to support accurate notetaking. The consultant will conduct a total of 5 FGDs with Afghan migrants and refugees. It is preferable to ensure a gender-balanced selection of respondents, as well as a diverse range of profiles (e.g., age, legal status, etc.). The estimated duration for each FGD is 60-90 mins.

For the FGDs, the following criteria should be implemented to select respondents:

- Respondents must be 18 years or older.

- Respondents must have travelled from Iran to Pakistan.

- Respondents must not have been interviewed by 4Mi in 2026.

The distribution will tentatively comprise of:

- 5 FGDS, with 6-8 participants per group.

- The groups will be the following

  - Group 1: Adult men (18+)

  - Group 2: Adult women (18+)

  - Group 3: Young men (18-24) or young women (18-24)

  - Group 4: Caregivers men or caregivers women traveling with children

  - Group 5: Recent arrivals men or recent arrivals women (after February 2026)

Key Informant Interviews

Data collection will take place face-to-face or over the phone, on paper or using Microsoft Excel or Word. If the Key informant consents, the KII may be audio-recorded to support accurate notetaking. The consultant will conduct a total of 20 KIIs with stakeholders. It is preferable to ensure a gender-balanced selection of respondents. The estimated duration for each KII is 45-60 mins.

The distribution will tentatively comprise of:

- Humanitarian actors and International/National organizations representatives (8-10 KIIs)

- Government officials (2-4 KIIs)

- Community leaders (6-8 KIIs)

After each FGD and KI, the consultant should send to MMC:

- Audio recordings of all KIIs and FGDs, where participants have provided informed consent.

- Raw field notes for all KIIs and FGDs, including observations recorded during data collection.

- Verbatim transcripts of all KIIs and FGDs in the original language, together with English translations.

- Based on MMC's quality review, if an interview or discussion does not meet the minimum quality standards, ensure that a replacement KII or FGD is conducted.

The consultant will be responsible for ensuring that enumerators have the appropriate equipment to conduct the interviews. The MMC 4Mi team will liaise with the consultant to provide feedback on data quality. The consultant will provide day-to-day support and supervision to enumerators throughout data collection.

It is anticipated that the consultant will be in regular contact with a primary contact point from the MMC team to keep up with the timeline that will be finalized during the inception phase. The MMC contact point will take responsibility for ensuring timely responses to drafts and inputs to the consultant.

# Deliverables

The consultant will submit the following deliverables:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1 Desk review | Presentation of desk review and inception report | 1. Conduct a brief desk review to refine sampling locations and ensure alignment with the scope of the study. 2. Submit an inception report (2-3 pages) outlining: - Scope of the study - Sampling criteria and locations for data collection - Survey implementation work schedule - Ethical considerations - List of relevant organizations for referral, in case respondents request information on services (the consultant will provide contact information but will not directly provide services) - Potential challenges, risks and mitigation strategies - Project team composition - Complaints and feedback mechanism | 1 week |
| Phase 2 Data collection | 5 FGDs and 20 KIIs | - Translation of the tool to Dari, Pashto and Urdu - Training of enumerators - Field visits - Testing of the tools - Collect 5 FGDs and 20 KIIs - Submit data after the completion of each interview | 2 weeks |
| Phase 3 Field Report | Presentation of field report detailing data collection process | - Document how the data collection was conducted, including adherence to the work plan and inception report, and any deviations - Outline challenges encountered during fieldwork (e.g., logistical, operational, or methodological) - Describe lessons learned regarding interview implementation, enumerator performance, and field management - Provide recommendations for improving future similar data collection exercises - Compile any operational notes, observations, or best practices that can inform MMC or partners for subsequent surveys - Ensure all documentation is complete, organized, and submitted according to MMC requirements | 1 week |

# Duration, timeline, and payment

Timeline

The following key activities and steps will be included in the consultant’s work plan:

- Completion of a brief inception report, which outlines, with demonstration of feasibility: an agreed sampling strategy that suits the objectives of the data collection in Pakistan, based on demographic characteristics in addition to pre-defined MMC sampling criteria; and proposed survey locations;

- Validation of the inception report by MMC and consultant’s integration of any feedback before finalizing the methodology

- Translation of the training materials and tool; MMC will provide the training materials and the tool in an XLS/word and readable format for translation by the consultant

- Enumerator preparation and training: MMC will share existing training documentation and SOPs on surveying. Training can be adapted to the specific context and sampling framework in a country. If errors or inconsistencies are spotted by the MMC team while conducting the cleaning and validation, the consultant is expected to provide this feedback to enumerators and conduct any relevant re-training

- Qualitative data collection (5 FGDs and 20 KIIs) in Pakistan

- Based on MMC's quality review, if an interview or discussion does not meet the minimum quality standards, ensure that a replacement KII or FGD is conducted.

- Submission of the field report outlining the data collection process

Duration

The total number of working days should not exceed four (4) weeks for the hired consultant. The consultant shall be prepared to complete the assignment no later than October 24, 2026.

Estimated start date of consultancy: September 27, 2026

Estimated end date of consultancy: October 24, 2026

Payment

Payments are subject to satisfactory quality validation by MMC teams, according to the following schedule:

30% upon validation of the inception report.

30% at the submission of 50% of the validated surveys.

40% at the submission of the total number of validated surveys and the validation of the field report.

# Proposed composition of team

- Project Coordinator

- Project Officer

- Enumerators

# Eligibility, qualification, and experience required

## Essential:

Please refer to Section B – Technical Evaluation of the RFP Invitation Letter.

## Desirable:

Pakistan-based consultants, research groups, or organizations will be strongly preferred.

# Technical supervision

The selected consultant will work under the supervision of the MMC Manager for the Middle East and Asia and the MMC Regional Research and Data Specialist.

# Location and support

Pakistan.

The Consultancy Company will provide its own equipment, i.e. computers and mobile telephones.

# Travel

The consultant is expected to have a presence in the selected locations during the data collection phase in order to monitor data collection activities. The consultant will be, therefore, expected to arrange transportation, accommodation, insurance, and food and to make adequate provision for related expenses in the financial proposal.

# Submission process

Refer to the RFP Invitation Letter.

# Evaluation of bids

Refer to the RFP Invitation Letter.

The pilot can be carried out in-house, allowing enumerators to practice administering the tools and note-taking procedures without involving actual study participants

Gender of respondents to be determined based on feasibility and availability. The groups should not be mixed.

Gender of respondents to be determined based on feasibility and availability. The groups should not be mixed.

Gender of respondents to be determined based on feasibility and availability. The groups should not be mixed.