DRC

Terms of Reference (TOR)

for

Consultancy for developing a package to support operationalization of localisation in DRC’s country operations

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

To strengthen the operationalization of DRC’s ambition to localise the humanitarian response, DRC is commissioning the first phase of a consultancy to support country operations identify and operationalize ambitions for localisation that are: i) founded in the local context and organizational reality, ii) clearly defined and broken down into workable targets. This will be done by i) developing a package to support DRC’s Country Operations (CO) identify a localisation strategy, and ii) developing and piloting a roadmap framework to inform and support operationalization of the identified strategic ambitions. The consultancy includes the development of the strategy package and roadmap framework, and the testing of both in two model countries.

DRC is anticipating the consultancy to be followed by a phase II, which would i) adjust the localisation strategy package and roadmap framework based on lessons learned and support use of the framework in additional COs, ii) assess implications of localisation for DRC’s organisational structure at large and derive recommendations for regional and HQ set-up and resourcing. This work is not included in the ToR at  hand, and will be tendered separately, but in conjunction with phase I.

# Background

DRC has a long tradition of being a self-implementing organization, working across the nexus and engaging in emergency, durable solutions and longer-term programming related to addressing root causes of displacement. In recent years, a move has been made towards localization of humanitarian and development interventions, with a view to increasing and improving engagement with local actors and systems. This move is comprising variations from country to country.

Partnerships is recognized as an important strategic priority for DRC and is enshrined as such in one of the Foundational Strategic Priorities in DRC’s Strategy 2025 that states a focus on enhancing equitable partnerships with local actors to achieve increased protection and enhanced inclusion of people affected by conflict and displacement. The organizational principle ‘Go local’ is one of five guiding principles for DRC’s strategic direction. A Civil Society Engagement Strategy has existed since 2020. DRC became a signatory to the Grand Bargain in 2021, thereby reinforcing our commitment to the localisation agenda.

At HQ level, DRC has a civil society engagement team, currently consisting of three staff. Partnerships with local authorities (duty bearers) and local private sector actors are an integral part of DRC’s localisation approach, which are covered by specialists in DRC’s durable solutions platform, innovation team and the global Economic Recovery team. A review of the past 10 years’ technical capacity assistance to duty bearers in Europe has recently been conducted. A separate consultancy to map out and derive methodologies from DRC’s work with duty bearers is being planned for Q2-3 2023. The consultancy at hand will take all three types of local actors into due consideration and base the work on existing knowledge and capacity in DRC.

## A decentralized organisation

DRC places value on being a decentralized organisation with a high level of autonomy in decision-making vested in Country Operations and Regional Offices (COs and ROs). An organisational transformation in 2022 aimed at strengthening and streamlining capacities and accountabilities and made ROs the main entry point for COs for technical support and decision-making in most operational areas. HQ oversees organizational finances and risk management and provides programmatic and strategic direction and guidance to ROs within DRC’s five sectors. This means that COs develop their own contextual strategies, raise their own funds and are largely able to be agile and flexible as long as they operate in accordance with the topline global strategic and programmatic frameworks and priorities as well as compliance policies and frameworks.

## Strengths and barriers to localisation

An 18-months learning journey finalised in 2022 identified key strengths and barriers to DRC’s engagement with civil society. Recognized strengths include a growing leadership buy-in and inclusion of engagement with civil society, duty bearers and the private sector in strategies across DRC. Several countries have dedicated staff resources and innovative ways of partnering are emerging. DRC’s reliance on project grants is a significant barrier. Strategic partnerships with Danida and SIDA (about 15% of the total budget) enable flexibility and long-term planning, however, DRC’s funding is mostly short-term project based. DRC’s structures, systems and processes are designed to execute projects directly and in accordance with donor requirements in a risk reducing manner. To this end, DRC as a ‘system’ is geared to engaging in transactional partnerships and supplier-like relationships with local actors more than supporting a transition towards local capacity and leadership. With this consultancy, DRC aims to support COs in meeting their localisation targets and ambitions, based on where they find themselves, contextually, organisationally and operationally, on the path to localisation.

# Objective of the consultancy (phase 1)

## Localisation strategy package

A package that can be used independently by all COs to develop their localisation strategy is developed. The package includes tools, guidance and formats towards developing a strategy that defines the CO’s targets and key strategic and programmatic priorities related to localisation. It also includes a workshop package, consisting of materials (agenda, presentations, method suggestions) needed for country offices to plan and conduct the workshops necessary to arrive at a localisation strategy in a participatory manner.

## Localisation Roadmap Framework

An analytical framework that builds on the localization strategy package is developed. The roadmap framework contains guidance on what questions to answer and how to answer them to successfully identify a roadmap towards operationalizing the identified localization strategy and targets. The roadmap framework will help COs identify and decide the organisational and operational changes needed towards realising their localisation ambition.

- Engagement with pilot COs

Liaison with, support to and facilitation of strategy development and development of roadmap with COs in Kenya and Burkina Faso, with the aim of ensuring the tools are feasible and significantly inform and support the CO’s journey towards localisation.

# Scope of work and Methodology

The consultancy is focused on strategy development and operationalization of localisation at country level. The role of the regional office in terms of providing leadership for change, programmatic leadership as well as technical expertise to support COs and mandate to make decisions, must be drawn in as relevant, paying attention to the newly implemented organisational structure. The role and function of HQ including global advisors may be drawn in as a result of specific findings at the level of RO, however paying attention to not replicating already known findings and recommendations identified in background documents.

It must be considered that country operations have a high workload. Despite the complexity of the area of inquiry, guidance and tools developed need to be as simple as possible and easy to use for COs without necessitating an external facilitator to support.

## Localization Strategy Package

The strategy package is meant to facilitate and guide processes that enable COs to answer the following questions:

- What are the specific localization targets of our CO (these might be specified per sector or platform (Emergency, Durable Solutions, Root Causes)?

- What strategic decisions around a specific response must be made to enable a localized approach?

- Are there areas where direct implementation must remain a main modality, and if so, why?

The package will take the key aspects of localisation into consideration:

- Partnerships

- Leadership

- Coordination and complementarity

- Participation

- Policy Influence and Advocacy

- Capacity

- Funding

The package will include materials (formats, tools, guidance) required for conducting the necessary processes to arrive at a contextualized localization strategy at country level:

- A baseline tool to provide COs with an understanding of where they are in the process towards localisation, what works and what needs to change or improve. The baseline tool should draw on, but not be limited to, existing literature on measuring localisation.

- Participatory analytical tools and exercises to identify country level strategic and programmatic priorities

- A strategy template with guiding notes

This will include a particular focus on supporting decision-making on direct vs. partner implementation modalities to enable COs to decide (and document the decision) on whether, where, how and why direct implementation remains part of a given CO’s portfolio.

In addition, the consultant will provide a facilitator’s package, including Power Point presentation, session plan incl. methods, handouts, background documents as relevant.

The Strategy Package must build on and complement – not duplicate – existing core analysis tools used by DRC.

## Localization roadmap framework

The roadmap framework is meant to enable COs to answer two overall questions that might be possible to work on independently from each other:

- How does our CO become prepared for the identified localization ambitions?

- What does localisation mean for the CO’s operational practices in the longer term?

The roadmap framework will enable COs to lay out a change process in their operation towards achieving the targets and ambitions in their localization strategy. It will include exploration of the contextual and financial trends that influence the CO’s operations; how the CO’s financial strategy, funding structure and funding strategy hinder or support localisation; and how favourable existing programme strategies, systems, structures, skills and culture are with regard to achieving the specific and timebound localization targets laid down in the localisation strategy.

The roadmap framework should support identification of changes within functions that are vital in ensuring a quality response to conflict and displacement as well as daily running of the CO. The focus is on needed adaptations to programmatic priorities, design and management as well as the daily operations and organisational adaptations that will make this possible. Support services (Finance, Supply Chain, HR) are considered vital operational areas to enable localisation ambitions. The roadmap framework will include an aspect of the financial implications for COs when they pass on more funding to local partners, thereby enabling decisions on resource adaptions.

The roadmap will look different from country to country, and the framework must therefore allow for and guide relevant adaptations.

## Collaboration with and support to two COs

Two COs, Kenya and Burkina Faso, will act as liaison partners through the process of developing the strategy package and the roadmap framework and as pilot countries for their subsequent application.

## Anticipated phase II: organizational model(s)

The development of model options on how DRC at large could adapt its structures, systems, and processes in scenarios with an increasing portfolio of our work done in partnerships with or in support of local actors is envisioned. This includes a modelling of specific changes in structures and processes needed across the different levels of the organization – HQ, Regional Offices, and Country Operations. Phase II will be based on the knowledge gained from working in the two pilot countries, combined with an adapted roadmap framework to be applied by HQ and Regional Office. The model options will feed into DRC’s consolidation of the organisational transformation executed in 2022.

Phase II is expected to include the review of the localisation strategy package and roadmap framework, as well as support to two additional countries in applying the tools.

It is envisaged for 2024 and will be tendered out separately.

## Methodology

The consultant is expected to apply a participatory approach. A methodology should be put forward in the technical proposal.

A combination of qualitative and quantitative methods will be used, and systematic inclusion of local partners with various capacities and types of relationships with DRC should be ensured.

To maintain ownership and participation, the consultant will to the extent possible play a role as a process facilitator and support the CO staff and management in applying the developed tools. This must be balanced with time and resources available in the CO. The approach throughout the assignment should be participatory, and as many staff as possible should contribute and participate actively, beyond existing departmental demarcations.

The roadmap framework will be anchored in organizational analysis or organisational assessment methodology and draw upon analytical frameworks needed to understand the external environment, strategy, financial resources, leadership, culture, structure, systems, skills, motivation and performance related to the localisation ambition. Importance should be placed on specificity in terms of activity, roles, responsibilities, costing and communication.

# Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Expected deliverables (in anticipated order of delivery) | Indicative description tasks | Expected timeframe | Expected deadline | Payment upon delivery |
| --- | --- | --- | --- | --- |
| 1) Inception report describing methodology and work plan | Desk work: Document review, interviews, submission of inception report for review | 3 working days | End of August 2023 | 15% |
| 2) Development of localisation strategy package and localisation roadmap framework | Desk work: tool development in liaison with DRC counterparts | 20 working days | End of September 2023 | 35% |
| 3) Support to two COs applying strategy package and roadmap framework | Field work including travel to Kenya and Burkina Faso. Includes 4 days for a parallel revision/adaptation of the developed tools and documents, based on learning from the pilot application. | 32 working days | As per agreed timeline, no later than end of October 2023 | 50% |

# Duration, timeline, and payment

The total expected duration to complete the assignment is 55 working days.

The consultant shall be prepared to complete the assignment no later than October 31st 2023.

# Proposed Composition of Team

The consultant is expected to include a proposition for how the company will meet the qualifications required in the ToR.

# Eligibility, qualification, and experience required

## Essential:

- Extensive expertise in organisational analysis and organisational change management or processes within humanitarian organisations

- Subject matter expertise within localisation and partnerships in humanitarian and development aid

- Profound understanding of the relationship between the strategic vision to localise and the risk and compliance environment that localisation efforts must navigate in.

- Experience in data collection and analysis applying qualitative and participatory methods, derived in a humanitarian context.

- Excellent process facilitation and relational skills

- Written and spoken proficiency in English expected, proficiency in French a strong advantage

## Desirable:

- Experience in financial strategy planning

- Experience working in fragile contexts

# Technical supervision

The selected consultant will work under the supervision of:

Civil Society Partnership Compliance Coordinator, Helena Brønserud Christensen, helena.christensen@drc.ngo

# Location and support

Borgergade 10, Copenhagen K

The Consultant will provide her/his own computer and mobile telephone

# Travel

Travel to Kenya and Burkina Faso will be included. See also deliverables.

The Consultant is expected to arrange transportation, accommodation, insurance, food and to make adequate provision in the Financial Proposal.

# Submission process

Please refer to the tender dossier.

# Evaluation of bids

Please refer to the tender dossier.

Throughout this document and in DRC at large, the wording “local actors and systems” always includes local civil society, authorities, and private sector actors. Who we work with, how and why in a given context will vary.