Terms of Reference (TOR)

for

H2H Network - MEAL Consultancy

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Who is the H2H Network?

H2H stands for ‘humanitarian to humanitarian.’ The concept refers to humanitarian organisations who provide technical services and resources to other humanitarian actors rather than directly to crisis-affected populations. The range of specialized services that H2H actors provide relate to data, information and analysis; community engagement and accountability; security, logistics and programme support as well as quality and professionalisation.

The H2H Network brings together high-quality, independent humanitarian service providers who bring cross-cutting technical expertise in service of the broader humanitarian community. Services and resources produced by H2H organizations are free and accessible to all humanitarian actors, thus serving as common goods for the aid sector. The network emerged following the World Humanitarian Summit (WHS) in 2016 and is now a growing network of over 60 member organisations.

The H2H Network is hosted by the Danish Refugee Council (DRC) in Geneva, Switzerland.

# Background

As a core pillar of its strategy the H2H Network manages a Fund which is activated in response to specific humanitarian crisis, to allow H2H organisations to rapidly access financial resources and provide specialized services and resources to operational agencies, with the aim of improving quality, effectiveness and accountability in the response.  To do so, the H2H Network works with its members and other stakeholders to identify key gaps and priorities in the response and to put together an integrated package of support services.

Projects funded by the H2H Network are short-term (typically 4-6 months) and are implemented at the onset of the crisis, with the goal to maximise the impact of H2H services and resources during the emergency phase.

The H2H Network has activated its Fund four times in 2022/2023, to address complex humanitarian crises caused by conflicts and natural disasters, including the floods in Pakistan (2022), the drought in the Horn of Africa (2022), the earthquake in Türkiye and Syria (2023) and the conflict in Sudan (2023).

# Objective of the consultancy

As part of its monitoring, evaluation and learning activities, the H2H Network aims to measure and document how the services and resources produced by its member organisations contributed to improving the quality, effectiveness and accountability of the humanitarian response in the contexts where it activated its Fund.

To this end, the specific purpose of this consultancy is to compile evidence and produce learning by production a series of four standalone case studies exploring the outcomes produced by the H2H Fund activations in Pakistan, the Horn of Africa, Türkiye and Syria and in Sudan.

# Scope of work and Methodology

A package of MEAL resources for the H2H Fund has already been developed and include: a MEAL framework; a series of templates to collect information across multiple sources (narrative project reports, learning workshop, questionnaire for key informant interviews); a coding table to compile and process data; a case study template to synthetise and analyse evidence and learning. The consultant will be expected to use the MEAL resources which have already been developed.

The main tasks are outlined below:

- Review existing evidence, including 1) narrative reports produced by member organisations at the end of their projects and 2) minutes and videorecording of the learning workshop facilitated by the H2H Network at the end of each Fund activation.

- Collect additional evidence by conducting interview with key informants, based on humanitarian actors and stakeholders identified by the H2H Network and its members.

- Compile and process evidence from all three information sources (narrative reports, learning workshop, key informant interviews) into a qualitative coding table.

- Produce a case study to present key evidence and learning about how each H2H Fund activations contributed to quality, effectiveness and accountability in the humanitarian response to crises.

The table below provide an estimation of the number of days required to successfully complete this consultancy:

| Task | Days by Fund activation | Total number of days |
| --- | --- | --- |
| Review existing evidence by: - Reading background documents - Reading narrative reports for each project - Reviewing document and recording from the learning workshop | 2 | 8 |
| Collect additional evidence by: - Conducting interviews with key informants - Writing interviews notes | 3 | 12 |
| Compile and process information by: - Review and filling-in the coding table with information across multiple sources | 2 | 8 |
| Produce case studies by: - Drafting the case studies - Incorporating feedback and finalizing the case studies | 3 | 12 |
| Total | 10 | 40 |

# Deliverables

For each of the four Fund activations the Consultant will submit the following deliverables:

- Notes of interviews with key informants

- Coding table with information across all three information sources (narrative reports, learning workshops, key informant interviews)

- Case studies

# Duration and timeline

The consultancy will start in July and will end in December 2023.

# Experience and qualifications

The individual consultant or team should possess:

- Good knowledge of humanitarian responses to crises, including driving factors, operational priorities, cross-cutting issues, contextual challenges, stakeholders, coordination architecture etc.

- Technical expertise on monitoring, evaluating and promoting learning in the context of humanitarian programs and interventions.

- Prior experience in conducting qualitative measurement exercise, including the production of case studies.

- Excellent research and writing skills in English

- Knowledge of the H2H Network and its member organisations is an advantage.

# Technical supervision

The selected consultant will work under the supervision of the H2H Fund Coordinator.

# Location and support

The consultant will be based remotely and use their own IT equipment and computer.

# Travel

No travel is required for this consultancy.

# Submission process

Interested individuals or teams should submit the following documents to tender@drc.ngo:

- Resume(s)

- Cover letter

- 3 relevant work samples (case study, qualitative research, previous publications etc.).

- A cost offer (RFQ document) consisting of an inclusive daily fee for the proposed number of working days.

- Completed DRC Supplier Profile Registration Form

# Evaluation of bids

The evaluation is made on a technical and financial basis.

The proposed technical offers by bidders will be evaluated using the following criteria:

| Type | Weight |
| --- | --- |
| Demonstrated expertise and experience against the stated requirements. | 75 % |
| Financial proposal | 25% |

# Contact person

For any inquiries related to this RFP, kindly contact Yannick Creoff, H2H Network, Fund Coordinator, yannick@h2hnetwork.org