DANISH REFUGEE COUNCIL

TENDERING DOCUMENTS FOR

THE COMPETITIVE TENDERING OF

CONSTRUCTION WORKS

Installation of 3 solarized farming irrigation system Works in Mandera

| Tender Reference Number | Tender Description | Quantity |
| --- | --- | --- |
| ITB/ 356781/BOR/2025 | Installation of 3 solarized farming irrigation system | Lot 1 |

| Line | Item | Time, date, address as appropriate |
| --- | --- | --- |
| 1 | Tender published | 11/08/2025 |
| 2 | Closing date for clarifications | 25/08/2025 1700hrs EAT |
| 3 | Site visit | Tenderers to make private arrangements at own convenience |
| 4 | Closing date and time for receipt of tenders | 04/09/2025 1000hrs EAT |
| 5 | Tender Opening Date and time | 04/09/2025 1100EAT |

Table of Contents

Section 1 	Instructions to Bidders (ITB)	1

Table of Clauses	1

Section 2	BIDDING DATA	9

Section 3	CONDITIONS OF CONTRACT	11

Table of Clauses	11

Section 4 	CONTRACT DATA	22

Section 5	STANDARD FORMS	25

Table of Standard Forms	25

Standard Form A:	Contractor's Bid	26

Standard Form B:	Qualification Information	27

Standard Form C:	Letter of Acceptance	30

Standard Form D:	Agreement	31

Standard Form E:	Bid Security Form	33

Standard Form F:	Performance Security Form	34

Section 6 	SPECIFICATIONS	36

Section 7 	DRAWINGS	38

Section 8 	BILL OF QUANTITIES	39

# Section 1 	Instructions to Bidders (ITB)

### Table of Clauses

| 1. Scope of Bid……………………………………………………….2 2. Qualification of Bidder 2 3. One Bid per Bidder 2 4. Cost of Bidding 2 5. Site Visit 2 6. Content of Bidding Documents ………………………….2 7. Clarification of Bidding Document........................3 8. Language of Bid 3 9. Documents Comprising Bid 3 10. Bid Prices …. 3 11. Currency of Bid & Payment 4 12. Bid Validity 4 13. Format and Signing of Bid 4 14. Sealing and Marking of Bid……...……………………….5 15. Deadline for Submission of Bids...…………………….5 16. Late Bids…………………………………………………………..5 | 17. Modification and Withdrawal of Bids...………………5 18. Bid Opening 5 19. Process to Be Confidential 5 20. Clarification of Bids 6 21. Examination of Bids and Determination of Responsiveness ………………..………….……………….6 22. Correction of Errors 6 23. Evaluation and Comparison of Bids………………….6 24. Award Criteria 7 25. DRC's Right to Accept any Bid to Reject any or all Bids………………………………………………………………….7 26. Notification of Award and Signing of the Agreement .7 27. Performance Security….....……………………………………7 28. Interim payment Payment………….…………………………………8 |
| --- | --- |

| - Scope of Bid | 1.1 The Danish Refugee Council (DRC) as defined in the Contract Data invites bids for the construction of Works, as described in the Contract Data. The name and identification number of the Contract is provided in the Contract Data. - The successful Bidder will be expected to complete the Works by the Required Completion Date specified in the Contract Data. |  |
| --- | --- | --- |
| - Qualification of the Bidder | 2.1 All bidders shall provide in Section 3, Forms of Bid and Qualification Information, a preliminary description of the proposed work method and schedule, including drawings and charts, as necessary. 2.2 To qualify for award of the Contract, bidders shall meet the following minimum qualifying criteria: (a) annual volume of construction work during past two years of at least the amount specified in the Bidding Data; (b) experience as prime contractor in the construction of at least one works of a nature and complexity equivalent to the Works over the last 2 years (to comply with this requirement, works cited should be at least 80 percent complete); (c) proposals for the timely acquisition or (own, lease, hire, etc.) of the essential equipment listed in the Bidding Data; and (d) A Project Manager with two years' experience in works of an equivalent nature and volume. |  |
| - One Bid per Bidder per facility | 3.1 Each Bidder shall submit only one Bid, either individually or as a partner in a joint venture. A Bidder who submits or participates in more than one Bid will be disqualified. Partners in a joint venture shall be jointly and severally liable for the execution of the Contract. |  |
| - Cost of Bidding | 4.1 The Bidder shall bear all costs associated with the preparation and submission of his Bid, and the DRC will in no case be responsible or liable for those costs. |  |
| - Site Visit | 5.1 The Bidder, at the Bidder's own responsibility and risk, is encouraged to visit and examine the Site of Works and its surroundings and obtain all information that may be necessary for preparing the Bid and entering into a contract for construction of the Works. The costs of visiting the Site shall be at the Bidder's own expense. |  |
| - Content of Bidding Documents | 6.1 The set of bidding documents comprises the documents listed in the table below and any addenda issued. Section 1 Instructions to Bidders 2. Bidding Data 3. Conditions of Contract 4. Contract Data 5. Forms of Bid and Qualification 6. Specifications 7. Drawings 8 Bill of Quantities or Activity Schedule for lump sum contracts |  |
| - Clarification and Amendments of Bidding Documents | - A prospective bidder may request the DRC in writing for clarifications and queries on the bidding documents via email to procurement.ken2@drc.ngo Bids shall not be sent to the above email. The DRC shall respond to such requests if it receives those 15 days prior to the deadline for the submission of bids. All questions during the tender period, as well as the associated answers, will be accessed by all suppliers through the following link: ITB- 356781-BOR-2025 Installation of 3 solarized farming irrigation system - Similarly, prior to the submission of the deadline, the DRC may modify the bidding documents by issuing addenda on the same link above. |
| - Language of Bid | 8.1 All documents relating to the Bid and contract shall be in the language specified in the Contract Data. |
| - Documents Comprising the bid | 9.1 The Bid submitted by the Bidder shall comprise the following: (a) The Bid (in the format indicated in Section 2); (b) priced Bill of Quantities or priced Activity Schedule; - Qualification Information Form and Documents; - If the Bidding Data specifies a Bid Security is required, this must be provided in the format provided and shall be for a value of not less than 2% (two percent) of the offer value and shall be valid for at least 30 days past the validity period. and any other materials required to be completed and submitted by bidders, as specified in the Bidding Data. |
| - Bid Prices | 10.1 The Contract shall be for the whole Works, as described in Sub-Clause 1.2, based on the priced Bill of Quantities or priced Activity Schedule for lump sum contracts submitted by the Bidder. The type of contract lump sum based on Activity Schedule) will be specified in the Bidding Data. 10.2 The Bidder shall fill in rates and prices for all items of the Works described in the Bill of Quantities (for lump sum contracts, described in the drawings and specifications and listed in the Activity Schedule). Items for which no rate or price is entered by the Bidder will not be paid for by the DRC when executed and shall be deemed covered by the other rates and prices in the Bill of Quantities or Activity Schedule. 10.3 All duties, taxes, and other levies payable by the Contractor under the Contract, or for any other cause, as of the date 15 days prior to the deadline for submission of bids, shall be included in the rates, prices, and total Bid price submitted by the Bidder (for lump sum contracts, "the rates and prices" are not applicable). 10.4 The rates and prices (or the lump sum price) quoted by the Bidder shall be fixed for the duration of the Contract and shall not be subject to any adjustment on any account. |
| - Currency of Bid and Payment | 11.1 Prices shall be quoted in the currency specified in the Bidding Data. |
| - Bid Validity | 12.1 Bids shall remain valid for the period specified in the Bidding Data. The DRC may request that the bidders extend the period of validity for a specified additional period. The request and the bidders' responses shall be made in writing or by cable or by fax. A Bidder may refuse the request in which case he may withdraw his bid without penalty. A Bidder agreeing to the request will not be required or permitted to otherwise modify the Bid. |
| - Format and Signing of Bid | 13.1 The Bidder shall prepare one original of the documents comprising the Bid as described in Clause 6 of these Instructions to Bidders, with the Form of Bid In addition, the Bidder shall submit the bid by email to the following dedicated, controlled, & secure email address: tender.ken@drc.ngo |
|  | 13.2 When the bids are being emailed, the following conditions shall apply - The ITB number and Lot number shall be inserted in the Subject Heading of the email i.e “ITB/0356781/BOR/2025” - Bid documents required, shall be included as an attachment to the email in PDF, JPEG, TIF format, or the same type of files provided as a ZIP file. - Email attachments shall not exceed 4MB; otherwise, the bidder shall send their bid in multiple emails Failure to comply with the above may disqualify the Bid. 13.3 The Bid shall contain no alterations or additions, except those to comply with instructions issued by the DRC, or as necessary to correct errors made by the Bidder, in which case such corrections shall be initialled by the person or persons signing the Bid. 13.3 a) The Bid shall be typed or written in indelible ink and shall be signed by a person or persons duly authorized to sign on behalf of the Bidder. All pages of the Bid where entries or amendments have been made shall be initialled by the person or persons signing the Bid. |
| - Sealing and Marking of Bids | 14.1 The Bidder shall seal the original and all copies of the Bid in two inner envelopes and one outer envelope, duly marking the inner envelopes as “ORIGINAL” and “COPIES”. 14.2 The inner and outer envelopes shall (a) be addressed to the DRC at the address provided in the Bidding Data; (b) bear the name and identification number of the Contract as defined in the Bidding and Contract Data; and (c) Provide a warning not to open before the specified time and date for Bid opening as defined in the Bidding Data. 14.3 In addition to the identification required in Sub-Clause 14.2 the inner envelopes shall indicate the name and address of the Bidder to enable the Bid to be returned unopened in case it is declared late, pursuant to Clause 16.1. 14.4 If the outer envelope is not sealed and marked as above, the DRC will assume no responsibility for the misplacement or premature opening of the Bid. |
| - Deadline for Submission of Bids | 15.1 Bids shall be submitted to the indicated email address specified above no later than the time and date specified in the Bidding Data. - The DRC may extend the deadline for submission of bids by issuing an amendment in accordance with Clause 7, in which case all rights and obligations of the DRC and the bidders previously subject to the original deadline will then be subject to the new deadline. |
| - Late Bids | 16.1 Any Bid received by the DRC after the deadline prescribed in Clause 15 will be returned unopened to the Bidder. |
| - Modification and Withdrawal of Bids | 17.1 Bidders may modify or withdraw their bids by giving notice in writing before the deadline prescribed in Clause 15.1 17.2 Each Bidder's modification or withdrawal notice shall be sent via email in accordance with Clauses 14 and 15. 17.3 No Bid may be modified after the deadline for submission of Bids. 17.4 Withdrawal of a Bid between the deadline for submission of bids and the expiration of the period of Bid validity specified in the Bidding Data or as extended pursuant to Sub-Clause 12 will result in the bidder being disqualified from future bidding for a period of one year. - Bidders may offer discounts, or otherwise modify the prices of their bids by submitting Bid modifications in accordance with this clause, or included in the original Bid submission. |
| - Process to Be Confidential | 18.1 Information relating to the examination, clarification, evaluation, and comparison of bids and recommendations for the award of a contract shall not be disclosed until the award to the successful Bidder is announced. |
| - Clarification of Bids | 19.1 To assist in the examination, evaluation, and comparison of bids, the DRC may, at the DRC's discretion, ask any Bidder for clarification of the Bidder's Bid. The request for clarification and the response shall be in writing or by cable, telex, or facsimile, but no change in the price or substance of the Bid shall be sought, offered, or permitted except as required to confirm the correction of arithmetic errors discovered by the DRC in the evaluation of the bids in accordance with Cl. 23.2. |
| - Examination of Bids and Determination of Responsiveness | 20.1 Prior to the detailed evaluation of bids, the DRC will determine whether each Bid is substantially responsive to the requirements of the bidding documents. A substantially responsive Bid is one which conforms to all the terms, conditions, and specifications of the bidding documents, without material deviation or reservation. A material deviation or reservation is one (a) which affects in any substantial way the scope, quality, or performance of the Works; (b) which limits in any substantial way, inconsistent with the bidding documents, the DRC's rights or the Bidder's obligations under the Contract; or (c) whose rectification would affect unfairly the competitive position of other bidders presenting substantially responsive bids. 20.2 If a Bid is not substantially responsive, it will be rejected by the DRC, and may not subsequently be made responsive by correction or withdrawal of the nonconforming deviation or reservation. 20.3 Due diligence will be conducted for the submitted bids |

| - Correction of Errors | 21.1 Bids determined to be substantially responsive will be checked by the DRC for any arithmetic errors. Errors will be corrected by the DRC as follows: (a) where there is a discrepancy between the amounts in figures and in words, the amount in words will govern; and (b) Where there is a discrepancy between the unit rate and the line item total resulting from multiplying the unit rate by the quantity, the unit rate as quoted will govern. (c) If a bidder refuses to accept the correction his bid will be rejected, and the bidder disqualified from future bidding for a period of one year. |
| --- | --- |
| - Evaluation and Comparison of Bids | 22.1 The DRC will evaluate and compare only the bids determined to be substantially responsive in accordance with Clause 21. 22.2 In evaluating the bids, the DRC will determine for each Bid the evaluated Bid price by adjusting the Bid price as follows: (a) making any correction for errors pursuant to Clause 22 (b) excluding provisional sums and the provision, if any, for contingencies in the Bill of Quantities (or Activity Schedule for lump sum contracts), but including Day-work, where priced competitively; (c) Making appropriate adjustments to reflect discounts or other price modifications offered in accordance with Sub-Clause 17.5. 22.3 The DRC may waive any minor informality or non-conformity which does not constitute a material deviation, provided such waiver does not prejudice or affect the relative standing of any Bidder. Variations, deviations, and alternative offers and other factors which are in excess of the requirements of the bidding documents or otherwise result in unsolicited benefits for the DRC will not be considered in Bid evaluation. |
| - Award Criteria | - Subject to Clause 25, the DRC will award the Contract to the Bidder whose Bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid price, provided that such Bidder has been qualified in accordance with the Clause 2 provisions. |
| - DRC's Right to Accept any Bid and to Reject any or all Bids | 24.1 Notwithstanding Clause 24, the DRC reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all bids, at any time prior to the award of Contract, without thereby incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the DRC's action. |
| - Notification of Award and Signing of Agreement | 25.1 The Bidder whose Bid has been accepted will be notified of the award by the DRC prior to expiration of the Bid validity period by registered letter. This letter (hereinafter and in the Conditions of Contract called the “Letter of Acceptance”) will state the sum that the DRC will pay the Contractor in consideration of the execution, completion, and maintenance of the Works by the Contractor as prescribed by the Contract (hereinafter and in the Contract called the “Contract Price”). 25.2 The notification of award will constitute the formation of the Contract. 25.3 The DRC will send the successful Bidder the Agreement form provided in the bidding documents incorporating all agreements between the DRC and the successful Bidder. It will be sent to the successful Bidder within 15 days following the notification of award. Within 15 days of receipt, the successful Bidder will sign the Agreement and deliver it to the DRC. - Upon receipt of the signed Agreement from the Bidder, the DRC will promptly notify the other bidders that their bids have been unsuccessful. |
| - Performance Security | 26.1 If required and stated in the Bid Data sheet, within 18 (eighteen) days of the receipt of notification of award from the Purchaser, the successful Bidder shall furnish the performance security in accordance with the Conditions of Contract, in the Performance Security Form provided in the bidding documents, or in another form acceptable to the Purchaser. 26.2 Failure of the successful Bidder to comply with the requirement of ITB Clause 27 shall constitute sufficient grounds for the annulment of the award and forfeiture of the bid security, in which event the Purchaser may make the award to the next lowest evaluated Bidder or call for new bids. |
| - Advance Payment | 27.1 The DRC will not provide an Advance Payment but will provide interim payments and this will be subject to measured works. For receiving the interim Payment, the Bidder shall make an estimate of executed work which MUST be certified by DRC project manager |

# Section 2	BIDDING DATA

This section should be filled out by the DRC before issuance of the bidding documents.

Instruction to Bidders Clause Reference

- All bidders shall provide bidding document, qualification information, a preliminary description of the proposed work method and schedule as necessary and all documents listed in clause 5

- In preparing the bid, bidders are expected to examine the documents constituting this ITB in details. Inadequate packing of information required will reduce legitimacy of your bid

- DRC reserves the right to negotiate, accept or reject any or all proposals and quotations at its sole discretion and to pursue or act further on any responses it considers advantageous.

- The contract will be awarded to the administratively and technically compliant tender that is the most economically advantageous, considering the quality of the services offered and the price of the tender.

- Tenders will be evaluated on the criteria listed below.

- Stage 1: Preliminary Bid Responsiveness Assessment

This will involve assessing whether bidders for works have complied with submission requirements and have also attached certified copies of mandatory eligibility and statutory documents. Evaluation at this stage will be conducted on Yes/No, and bidders are expected to show evidence of ALL required items to proceed to the next stage of evaluation

- Copy of Business certificate of Incorporation/Registration

- KRA Pin certificate and tax compliance

- Tender security from a reputable bank or insurance Company approved by IRA amounting Ksh.1,500,000 in favor of Danish Refugee Council (DRC) as indicated in the tender data sheet.

- Valid current Tax Compliance certificate from Kenya Revenue Authority

- Latest CR12 within 6 months

- National Construction Authority NCA 6 Water works

- National Construction Authority NCA 6 Civil works

- National Construction Authority NCA 6 Electrical works

- Valid Business permit/trade license

- Registration certificate with Engineers Board of Kenya (EBK) and EPRA certificate as Photovoltaic Engineer or Technician for the lead engineer with valid license

- Dully filled, signed and stamped standard form B – Qualification information (past experiences, contractor equipment etc.

- Detailed CV of all proposed key personnel

- Evidence of past experiences for at least 3 works contract of similar nature, value and complexity equivalent.  Any photos submitted should serve as supporting evidence and be tied to those contracts to avoid unverifiable submissions

- Construction Schedule or workplan (No specific format provided)

- At least 2 recommendation letters for similar works

- Dully filled, signed and stamped standard form E – Bid security form

- Annex A – supplier profile and registration form (filled, stamped and signed)

- Annex B- Supplier code of conduct form (filled, stamped and signed)

- Annual turnover sales of Kes 105,000,000 for any of the last three years.

Bidders who will not show evidence of all required items will not proceed to the next stage of technical evaluation

- Stage 2: Technical Evaluation Stage

Bids will be evaluated to ensure that they are substantially responsive to the technical specifications and contract conditions stated in the Tender Document.

Bidding documents under this evaluation will be scored against the following criteria

|  | Technical Criteria |  |  | POINT SCORE SCALE 1-10 Weighted score % |
| --- | --- | --- | --- | --- |
| 1 | WORK EXPERIENCE |  |  |  |
|  | Attach contract agreements/Purchase order including completion certificates from different firms as evidence. |  |  | 57% |
|  | 1.1 Similar projects and value of related works handled. |  |  |  |
|  | Any Four similar projects of equal or higher value of the project in the last five years. |  |  | 28% |
|  | Any Four similar projects of more than 50% and less than 100% of the value of the project in the last five years. |  |  | 17% |
|  | Any Four similar projects less than 50% the value of the project in the last five years. |  |  | 12% |
| 2 | KEY PERSONNEL |  |  | 20% |
|  | Technical skill in terms of human resource. Attach CVs and certified copies of academic & professional certificates and licenses detailing qualifications of 3 key personnel who shall be involved in this assignment. The persons must be working with the organization or has a signed undertaking to work with the firm by the time of submitting this tender. Each of the 3 personnel will be evaluated on the following parameters: |  |  |  |
|  | Project Engineer (Civil & Water Works): |  |  | 8% |
|  | BSc. Civil Engineering |  |  |  |
|  | Over 8 years’ experience working with similar project of similar contract value ( list in the CV the projects and value) |  |  |  |
|  | Registered with professional body ERB/IEK with valid license |  |  |  |
|  | Project Engineer (Electrical Works ) |  |  |  |
|  | BSc. Electrical Engineering |  |  | 8% |
|  | Over 8 years’ experience working with similar project of similar contract value (list in the CV the projects and value) |  |  |  |
|  | Registered with professional body ERB/IEK and with a possession of valid EPRA certification |  |  |  |
|  | Foreman |  |  | 4% |
|  | Diploma construction management/civil engineering |  |  |  |
|  | Over 4 years’ experience working with similar project of similar contract value (list in the CV the projects and value) |  |  |  |
|  | Registered with professional body (NCA) |  |  |  |
| 3 | PLANT AND EQUIPMENT |  |  | 12% |
| Relevant Equipment |  | Provide evidence showing if the equipment is owned/Leased (dump truck concrete mixer vibrator | Dump truck | 12% |
|  |  |  | Concrete mixer |  |
|  |  |  | Vibrator |  |
| 4 | WORK SCHEDULE |  |  | 5% |
|  | Detailed and realistic workplan | Detailed Program of works |  |  |
|  |  | Realistic implementation timeframe |  |  |
| 5 | FINANCIAL CAPACITY |  |  | 6% |
|  | 3 years certified audited financial reports (2022 ,2023 and 2024) |  |  |  |
|  | TOTAL |  |  | 100% |

The technical evaluation pass mark shall be 40 points and bidders who shall attain the pass mark will be subjected to tender price comparisons. Bidders who shall score below 40 points will be discontinued from further evaluation

- Stage 3: Financial Evaluation Stage

The financially will scored based on how the bidder’s price will vary with engineers estimate and will be scored against a maximum of 30 points

- Stage 4: Contract Award

Award the Contract to the bidder whose bid is determined to be substantially responsive to the tender documents and who has accumulated the highest score for in technical and financial evaluation

- This shall be a Lump Sum Contract based on Priced Bill of Quantities

- The currency in which the prices shall be quoted in Local currency/Kes

- The period of Bid validity shall be _180 days _________  days after the deadline for Bid submission specified in the Bidding Data.

- The number of copies of the Bid to be completed and returned

- The bids will be completed and submitted by emails to the following dedicated, controlled and secure email address tender.ken@drc.ngo and the following condition MUST be complied with

- The ITB No shall be inserted in the subject heading of the email

- The required bid documents shall be included as an attachment to thee email in PDF,JPEG, TIF format or the same file provided as ZIP file

- Email attachments shall not exceed 4MB; otherwise, the bidder shall send his bid in multiple emails.

Failure to comply with the above will lead to disqualification

- DRC will not be responsible for failure of the internet, server or any other hardware, or software used by either the bidder of DRC in the processing of emails

- Bid will be submitted electronically. DRC will not be responsible for non-receipt of bids submitted by email as part of the e-Tendering process

- The name and the identification number of the Contract is ITB/0356781/BOR/2025

- The Bidder, at the Bidder's own responsibility and risk, is encouraged to visit and examine the Site of Works and its surroundings and obtain all information that may be necessary for preparing the Bid and entering into a contract for construction of the Works. The costs of visiting the Site shall be at the Bidder's own expense Project Site Locations and GPS Coordinates are: BP1 (Lat 3.973713, Long 41.889940), Meygag (Lat 3.940663, Long 41.315260) and Girisa (Lat 3.943636, Long 41.238503) in Mandera

- The deadline for submission of bids shall be on 4th September  2025 at 1000hrs EAT  and bids shall be opened at 1 hour later (11.00hrs) at the same date and address.

- A Performance Security is required in the format provided in this document for a value of not less than (Usually 5% (five percent) of the contract value). This should be valid for 30 days past the contract completion period including 	any defects liability period or any warrantee period.

- The Interim Payment shall be limited to the total value of executed works certified by the DRC project manager minus 10%  the Contract Price (Retention).

# Section 3	    CONDITIONS OF CONTRACT

### Table of Clauses

| 1. Definitions 12 2. Language and Law 14 3. Communications 14 4. Subcontracting and other Contractors 14 5. Personnel 14 6. Contractor's Risks 14 7. Insurance 14 8. Contractor to Construct the Works 15 9. The Works to Be Completed by the 15 Completion Date 10. Safety 15 11. Program 15 12. Extension of the Completion Date 15 13. Delays Ordered by the DRC 15 14. Early Warning 16 15. Correction of Defects 16 16. Uncorrected Defects 16 17. Bill of Quantities 16 18. Changes in the Quantities 16 | 19. Payment Certificates 16 20. Payments 17 21. Compensation Events 17 22. Tax 18 23. Liquidated Damages 18 24. Interim Payment 18 25. Retention Money 18 26. Day works 18 27. Cost of Repairs 19 28. Completion and Take Over 19 29. Final Account 19 30. Termination 19 31. Payment upon Termination 20 32. Property 20 33. Release from performance 20 34. Resolution of Disputes 20 |
| --- | --- |

Conditions of Contract

| - Definitions | 1.1 Terms that are defined in the Contract Data are not also defined in the Conditions of Contract but keep their defined meanings. Boldface type is used to identify defined terms. Activity Schedule means the priced and completed schedule forming part of the Bid. Bill of Quantities means the priced and completed Bill of Quantities forming part of the Bid. Compensation Events are those defined in Clause 21 hereunder. The Completion Date is the date of completion of the Works as certified by the DRC, in accordance with Sub-Clause 28.1 The Contract is the Contract between the DRC and the Contractor to execute, complete, and maintain the Works. The name and identification number of the Contract is given in the Contract Data. The Contractor is a person or corporate body whose Bid to carry out the Works has been accepted by the DRC. The Contractor's Bid is the completed bidding document submitted by the Contractor to the DRC. |
| --- | --- |
|  | The Contract Price is the price stated in the Letter of Acceptance and thereafter as adjusted in accordance with the provisions of the Contract. Day works are additional, varied work inputs subject to payment on a time basis for the Contractor's employees and Equipment, in addition to payments for associated Materials and Plant. Days are calendar days; months are calendar months. A Defect is any part of the Works not completed in accordance with the Contract. The Defects Liability Period is the period named in the Contract Data and calculated from the Completion Date. Drawings include calculations and other information provided or approved by the DRC for the execution of the Contract. The DRC, as specified in the Contract Data, is the party who employs the Contractor to carry out the Works. The name of the DRC's representative authorized to deal with the Contractor is also given in the Contract Data. The Project Manager is the person named in the Contract Data (or any other competent person appointed by the DRC and notified to the Contractor, to act in replacement of the Project Manager) who is responsible for supervising the execution of the Works and administering the Contract. Equipment is the Contractor's machinery and vehicles brought temporarily to the Site to construct the Works. The Initial Contract Price is the Contract price listed in the DRC's Letter of Acceptance. The Required Completion Date is the date on which it is required that the Contractor shall complete the Works. The Required Completion Date is specified in the Contract Data. The Completion Date may be revised only by the DRC by issuing an extension of time or an acceleration order. Materials are all supplies, including consumable, used by the Contractor for incorporation in the Works. The Site is the area defined as such in the Contract Data. Specification means the Specification of the Works included in the Contract and any modification or addition made or approved by the DRC. The Start Date is given in the Contract Data. It is the latest date when the Contractor shall commence execution of the Works. It does not necessarily coincide with any of the Site Possession Dates. A Subcontractor is a person or corporate body who has a Contract with the Contractor to carry out a part of the work in the Contract, which includes work on the Site. Temporary Works are works designed, constructed, installed, and removed by the Contractor that are needed for construction or installation of the Works. A Variation is an instruction given by the DRC that varies the original Work requirement. The Works are what the Contract requires the Contractor to construct, install, and turn over to the DRC, as defined in the Contract Data. - This shall be a "Lump Sum Contract" based on priced Activity Schedule", as specified in the Contract Data. However, if a Government law or decree passed between the date 28 days before the submission of bids for the Contract and the Required Completion Date results in an increase in the price of labour and material, the DRC will adjust the contract price accordingly, provided that the Contractor shall submit documents satisfactory to the Project Manager proving that the requested increases are a result of Government laws or decrees. |
| - Language and Law | - The language of the Contract and the law governing the Contract are stated in the Contract Data. |
| - Communications | 3.1 Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered. |
| - Sub-contracting and other contractors | 4.1 The Contractor may subcontract with the approval of the Project Manager, but may not assign the Contract without the approval of the DRC in writing. Subcontracting shall not alter the Contractor's obligations. Not more than 50% of the work may be sub-contracted. The Contractor shall cooperate and share the Site with other contractors, public authorities, utilities, and the DRC. |
| - Personnel | 5.1 The Contractor shall employ the key personnel named in the Schedule of Key Personnel, as referred to in the Contract Data, to carry out the functions stated in the Schedule of other personnel approved by Project Manager. The Project Manager will approve any proposed replacement of key personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel listed in the Schedule. - If the Project Manager asks the Contractor to remove a person who is a member of the Contractor's staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within 72 hours and has no further connection with the work in the Contract. |
| - Contractor's Risks | - From the Starting Date until the Defects Correction Certificate has been issued, the risks of personal injury, death, and loss of or damage to property (including, without limitation, the Works, Plant, Materials, and Equipment) are Contractor's risks and adjacent property. |
| - Insurance | 7.1 The Contractor shall provide, in the joint names of the DRC and the Contractor, insurance cover from the Start Date to the end of the Defects Liability Period, in the amounts stated in the Contract Data for the following events which are due to the Contractor's risks: (a) loss of or damage to the Works, Equipment, Plant, and Materials; (b) loss of or damage to property (except the Works, Plant, Materials, and Equipment) in connection with the Contract; and (c) Personal injury or death. Third party liability. 7.2 Policies and certificates for insurance shall be delivered by the Contractor to the Project Manager for approval within 15 days of receipt by the Contractor of the DRC's Letter of Acceptance. All such insurance shall provide for compensation required to rectify the loss or damage incurred. If the Contractor fails to provide the required certificates, the contract shall be considered as annulled. The said Contractor shall be disqualified from participating in bidding for contracts for a period of one year. However, the DRC at his discretion may decide to extend the period for submission of insurance certificates or take out the insurance and deduct the cost of premiums from the Contractor's earnings. 7.3 Alterations to the terms of insurance shall not be made without the approval of DRC. |
| - Contractor to Construct the Works | - The Contractor shall construct and install the Works in accordance with the Specifications and Drawings. |
| - The Works to Be Completed by the Completion Date | - The Contractor may commence execution of the Works on the Start Date and shall carry out the Works in accordance with the Program submitted by the Contractor, as updated with the approval of the Project Manager, and complete them by the Required Completion Date. |
| - Safety | 10.1 The Contractor shall be responsible for the safety of all activities on the Site. |
| - Program | 11.1 Within the time stated in the Contract Data, the Contractor shall submit to the Project Manager for approval a Program showing the general methods, arrangements, order, and timing for all the activities in the Works. The Contractor shall update the Program at intervals no longer than the period stated in the Contract Data. The Project Manager's approval of the Program shall not alter the Contractor's obligations. The Contractor may revise the Program and submit it to the Project Manager again at any time. A revised Program shall show the effect of Variations and Compensation Events. |

| - Extension of the Completion Date | 12.1 The Project Manager shall extend the Completion Date if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Required Completion Date without the Contractor taking steps to accelerate the remaining work, which would cause the Contractor to incur additional cost. |
| --- | --- |
| - Delays Ordered by the Project Manager | 13.1 The Project Manager may instruct the Contractor to delay the start or progress of any activity within the Works. Delays or suspension of work by the Project Manager which increase the Contractor's costs shall be subject to equitable adjustments by the DRC. |
| - Early Warning | 14.1 The Contractor shall inform the Project Manager at the earliest opportunity of specific likely future events or circumstances that may adversely affect the quality of the work increase the Contract Price or delay the execution of the Works. The Project Manager may require the Contractor to provide an estimate of the expected effect of the future event or circumstance on the Contract Price and Completion Date. The estimate shall be provided by the Contractor as soon as reasonably possible. - The Contractor shall cooperate with the Project Manager in making and considering proposals for how the effect of such an event or circumstance can be avoided or reduced by anyone involved in the work and in carrying out any resulting instruction of the Project Manager. |
| - Correction of Defects | 15.1 The Project Manager shall give notice to the Contractor of any Defects before the end of the Defects Liability Period, which begins at Completion, and is defined in the Contract Data. The Defects Liability Period shall be extended for as long as Defects remain to be corrected. 15.2 Every time notice of a Defect is given, the Contractor shall correct the notified Defect within the length of time specified by the Project Manager's notice. |
| - Uncorrected Defects | 16.1 If the Contractor has not corrected a Defect within the time specified in the Project Manager's notice, the Project Manager will assess the cost of having the Defect corrected, and the Contractor will pay this amount, or the DRC shall recuperate these amounts by deduction from the amounts due to the contractor. |
| - Bill of Quantities | 17.1 The Bill of Quantities (for lump-sum Contracts Entire Clause 17 shall be replaced with a new Clause as indicated in the Contract Data) shall contain items for the construction, installation, testing, and commissioning work to be done by the Contractor. For Lump Sum contracts, payment activities schedule shall be listed. 17.2 The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work actually done at the rate in the Bill of Quantities for each item. |
| - Changes in the Quantities | 18.1 If the final quantity of the work done differs from the quantity in the Bill of Quantities for the particular item by more than 25 percent, provided the change exceeds 1 percent of the Initial Contract Price, the Project Manager shall adjust the rate to allow for the change. (For lump-sum contracts, this clause shall be substituted by a new clause as indicated in Contract Data). |
| - Payment Certificates | 19.1 The Contractor shall submit to the Project Manager bi-weekly statements of the estimated value of the work executed less the cumulative amount certified previously. 19.2 The Project Manager shall check the Contractor's executed work and certify the amount to be paid to the Contractor. 19.3 The value of work executed shall be determined by the Project Manager. 19.4 The value of work executed shall comprise the value of the quantities of the items in the Bill of Quantities completed. (For lump sum contracts, this Clause shall be substituted by a new Clause as indicated in the Contract Data). 19.5 The value of work executed shall include the valuation of Variations and Compensation Events. |
| - Payments | 20.1 Payments shall be adjusted for deductions for interim payments and retention. The DRC shall pay the Contractor the amounts certified by the Project Manager within 28 days of the date of each certificate. If the DRC makes a late payment, the Contractor shall be paid interest on the late payment in the next payment. Interest shall be calculated from the date by which the payment should have been made, up to the date when the late payment is made, at the rate of interest prevailing at the local banks for construction loans. 20.2 Items of the Works for which no rate or price has been entered in will not be paid for by the DRC and shall be deemed covered by other rates and prices in the Contract. |
| - Compensation Events | 21.1 The following shall be Compensation Events: (a) The DRC does not give access to a part of the Site by the Site Possession Date stated in the Contract Data. (b) The Project Manager orders a delay or does not issue Drawings, Specifications, or instructions required for execution of the Works on time. (c) The Project Manager instructs the Contractor to uncover or to carry out tests upon completed work, which is then found to have no Defects. (d) Other contractors, public authorities, utilities, or the DRC cause delay or extra cost to the Contractor. (e) The interim payment due is delayed. (f) The Project Manager unreasonably delays issuing a certificate of completion. If such an event occurs, then the Contract Price shall be equitably adjusted. |
| - Tax | 22.1 The Contractor is liable for all taxes in accordance with the laws of the DRC's country. However, the Project Manager shall adjust the Contract Price if taxes, duties, and other levies are changed between the date 28 days before the submission of bids for the Contract and the date of the last completion certificate. The adjustment shall be the change in the amount of tax payable by the Contractor, provided such charges are already not reflected in the Contract Price. |
| - Liquidated Damages | 23.1 The Contractor shall pay liquidated damages to the DRC at the rate per day stated in the Contract Data for each day that the Completion Date is later than the Required Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Contract Data. The DRC may deduct liquidated damages from any payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor's liabilities. |
| - Interim Payment | 24.1 The DRC shall make interim payment to the Contractor of the amounts stated in the Contract Data after certification of executed scope of works by the Contractor. |
| - Retention Moneys | 25.1 An amount, specified in the Contract Data, will be retained from each payment to the Contractor to assure performance of the work. This money will be paid out to the contractor upon completion and acceptance of the work and within 15 days of the issue by the Project Manager of the Defects Liability Certificate. |
| - Day-works | 26.1 If applicable, the Day-works rates in the Contractor's Bid shall be used for small additional amounts of work only when the Project Manager has given written instructions in advance for additional work to be paid for in that way. 26.2 All work to be paid for as Day-works shall be recorded by the Contractor on forms approved by the Project Manager. Each completed form shall be verified and signed by the Project Manager within two days of the work being done. 26.3 The Contractor shall be paid for Day-works as work is performed subject to obtaining signed Day-works forms. |
| - Cost of Repairs | 27.1 Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Correction periods shall be remedied by the Contractor at the Contractor's cost if the loss or damage arises from the Contractor's acts or omissions. |
| - Completion and Taking Over | 28.1 The Contractor shall request the Project Manager to issue a certificate of completion of the Works, and the Project Manager will issue such a certificate when he determines that the work is satisfactorily completed. The DRC shall take over the site and the works within seven days of the Project Manager's issuing of a certificate of completion. |
| - Final Account | 29.1 The Contractor shall supply the Project Manager with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Project Manager shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 15 days of receiving the Contractor's account if it is correct and complete. If it is not, the Project Manager shall issue within 15 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Project Manager shall decide on the amount payable to the Contractor and issue a payment certificate. |
| - Termination-action | 30.1 The DRC or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract. 30.2 Fundamental breaches of Contract shall include, but shall not be limited to, the following: (a) the Contractor stops work for 15 days when no stoppage of work is shown on the current Program and the stoppage has not been authorized by the Project Manager; (b) The Project Manager instructs the Contractor to delay the progress of the Works, and the instruction is not withdrawn within 15 days; or agreement reached on payments due contractor for cost of delay. (c) the DRC or the Contractor is made bankrupt or goes into liquidation other than for a reconstruction or amalgamation; (d) a payment certified by the Project Manager is not paid by the DRC to the Contractor within 30 days of the date of the Project Manager's certificate; (e) the Project Manager gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to correct it within 30 days determined by the Project Manager; (f) The Contractor has delayed the completion of the Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in the Contract Data. 30.3 When either party to the Contract gives notice of a breach of Contract to the Project Manager for a cause other than those listed under Sub-Clause 30.2 above, the Project Manager shall decide whether the breach is fundamental or not. 30.4 Notwithstanding the above, the DRC may terminate the Contract for convenience by giving the Contractor a thirty-day notice in writing. - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site within 15 days of the completion of the notice period. |
| - Payment upon Termination | 31.1 If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Project Manager shall issue a certificate for the value of the work done and Materials ordered less any interim payments received up to the date of the issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Contract Data. Additional Liquidated Damages shall not apply. If the total amount due to the DRC exceeds any payment due to the Contractor, the difference shall be a debt payable to the DRC. 31.2 If the Contract is terminated for the DRC's convenience or because of a fundamental breach of Contract by the DRC, the Project Manager shall issue a certificate for the value of the work done, Materials ordered, the reasonable cost of removal of Equipment, repatriation of the Contractor's personnel employed solely on the Works, and the Contractor's costs of protecting and securing the Works, and less interim payments received up to the date of the certificate. |
| - Property | 32.1 All Materials and Construction Equipment on the Site, Plant, Temporary Works, and Works shall be deemed to be the property of the DRC if the Contract is terminated because of the Contractor's default. |
| - Release from Performance | 33.1 If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of either the DRC or the Contractor, the Project Manager shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards for which an agreement has been reached. |
| - Resolution of Disputes | 34.1 The DRC and the Contractor shall make every effort to resolve amicably by direct informal negotiation any disagreement or dispute arising between them under or in connection with the Contract. If after thirty (30) days from the commencement of such informal negotiations, the DRC and the Contractor have been unable to resolve amicably a Contract dispute, either party may require that the dispute be referred for resolution to three independent qualified contractors, one chosen by the DRC and one chosen by the Contractor and the third chosen by an appropriate professional body, such as the Chamber of Commerce. The three should arrive at a solution satisfactory to the DRC and the Contractor. In case of further disagreement either party can take the matter to arbitration in accordance with the Law governing the Contract. The place where arbitration will take place will be stated in the Contract Data. |

# Section 4 	CONTRACT DATA

Except where otherwise indicated, all Contract Data should be filled in by the DRC (DRC) prior to issuance of the bidding documents. Schedules and reports to be provided by the DRC should be annexed.

Contract Clause

No.			Reference

1.	The DRC is:	[1.1]

Name:     DANISH REFUGEE COUNCIL

Address:  PO BOX 14762-00800 NAIROBI

Name of Authorized Representative:    SIMON NZIOKA

The Project Manager is:	[1.1]

Name:   SIMON GACHERU

Address:  P O BOX 14762 -00800 NAIROBI

Name of Authorized Representative: SIMON NZIOKA

2.	The name and identification number of the Contract is	[1.1]

ITB/0356781/BOR/2025 Installation of  Solarized farming Irrigation System in 3 site locations

3.	The Works consist of;

Lot 1- installation of solarized farming irrigation system in Mandera.

4.	The Start Date shall be   10/09/2025  		[1.1]

5.	The Required Completion Date for the whole of the Works shall be 01/12/2025	[1.1

6. 	Project Site Locations and GPS Coordinates aBP1 (Lat 3.973713, Long 41.889940), Meygag (Lat 3.940663, Long 41.315260) and Girisa (Lat 3.943636, Long 41.238503) in Mandera.  [1.1]

7.	This shall be a Lump Sum Contract based on Priced Bill of Quantities	[1.2]

8. 	The language of the Contract documents is   ENGLISH	[2]

9. 	The law that applies to the Contract is the law of   KENYA	[2]

10.  	The following documents are also part of the Contract:	[5]

- The Schedule of Key Personnel

12.  	The period for submission of the Program is 30 days from the date of signature	[11]

of Agreement.

13.  	The Defects Liability Period is 6 months.	[15]

14.  	In case of lump sum contracts, clause 17 shall be replaced by the following	[17]

new clause 17.

17	Activity Schedule

17.1	The Contractor shall provide updated Activity Schedules within 14 days of being instructed by the DRC.  The activities on the Activity Schedule shall be coordinated with the activities on the Program.

17.2	The Contractor shall show delivery of Materials to the site separately on the Activity Schedule if Payment for Materials on site shall be made separately."

15.  	In case of lump sum contracts, clause 18.1 shall be replaced by the following:	[18]

18.1	The Activity Schedule shall be amended by the Contractor to accommodate changes of program or method of working made at the Contractor's own discretion.  Prices in the Activity Schedule shall not be altered when the Contractor made such changes to the Activity Schedule."

19.4	The value of work executed shall comprise the value of completed activities in the Activity Schedule."

17.  	The Site Possession Date shall be    15/09/2025	 [21]

[If the Site is made available by section, the different dates should be listed here.]

20.  	The amount of interim payment will be based on measured and certified works by DRC project manager	[24]

21.  	The amount of retention money will be 10% of the total contract amount.

23.  	The place of arbitration is   NAIROBI	[34]

# Section 5	STANDARD FORMS

### Table of Standard Forms

A. Contractor's Bid25 B. Qualification Information 26 C. Letter of Acceptance 28 D. Agreement 29 - Bid Security 30 - Performance Security 32

### Standard Form A:	Contractor's Bid

Notes on Form of Contractor's Bid The Bidder shall fill in and submit this Bid form with the Bid.

__________________________________ [date]

To: _______________________________________________________ [name of DRC]

Address: ____________________________________________________ [insert address]

_____________________________________________________________________________

We offer to execute the _______________ [name and identification number of Contract] in accordance with the Conditions of Contract accompanying this Bid for the Contract Price of ________________ [amount in numbers and words] (________________________________) [name of currency] _______________________________).

This Bid and your written acceptance of it shall constitute a binding Contract between us. We understand that you are not bound to accept the lowest or any Bid you receive.

We hereby confirm that this Bid complies with the Bid validity required by the bidding documents and specified in the Bidding Data.

Authorized Signature: ________________________________________________________________

Name and Title of Signatory: ________________________________________________________________

Name of Bidder:

________________________________________________________________

Address:

_________________________________________________________________

### Standard Form B:	Qualification Information

Notes on Form of Qualification Information The information to be filled in by bidders in the following pages will be used for purposes of post qualification as provided for in the Instructions to Bidders. This information will not be incorporated in the Contract.

1.	Individual Bidders or Individual Members of Joint Venture

1.1	Constitution or legal status of Bidder		[attach copy]

Place of registration:		_______________________________

Principal place of business:	_______________________________

1.2	Work performed as prime Contractor on works of a similar nature and volume over the last two years.  Also list details of work under way or committed, including expected completion date.

| Project name and country | Name of client and contact person | Type of work performed and year of completion | Value of contract |
| --- | --- | --- | --- |
| ________________ ________________ ________________ ________________ ________________ ________________ [etc.] | ___________________ ___________________ ___________________ ___________________ ___________________ ___________________ | __________________________ __________________________ __________________________ __________________________ __________________________ __________________________ | ______________ ______________ ______________ |

1.3	Major items of Contractor's Equipment proposed for carrying out the Works. List all information requested below.

| Item of equipment | Description, make, and age (years) | Condition (new, good, poor) and number available | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- | --- |
| _________ _________ _________ [etc.] | _______________ _______________ _______________ | ____________________ ____________________ ____________________ ____________________ ____________________ ____________________ | ____________________________ ____________________________ ____________________________ |

1.4	Qualifications and experience of key personnel proposed for administration and execution of the Contract.

| Position | Name | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- | --- |
| Project Manager ___________________ ___________________ ___________________ ___________________ ___________________ [etc.] | __________________________ __________________________ __________________________ __________________________ __________________________ | ________________ ________________ ________________ ________________ ________________ | _________________ _________________ _________________ _________________ _________________ |

1.5	Proposed subcontracts and firms involved.

| Sections of the Works | Value of subcontract | Subcontractor (name and address) | Experience in similar work |
| --- | --- | --- | --- |
| _________________ _________________ _________________ [etc.] | _______________ _______________ _______________ | ____________________ ____________________ ____________________ ____________________ ____________________ ____________________ | ________________________ ________________________ ________________________ ________________________ ________________________ ________________________ |

1.6	Information on current litigation in which the Bidder is involved.

| Other party(ies) | Cause of dispute | Amount involved |
| --- | --- | --- |
| _______________________ _______________________ _______________________ _______________________ | ________________________ ________________________ ________________________ ________________________ | ________________ ________________ |

1.7	Proposed Program (work method and schedule). Descriptions, drawings, and charts, as necessary, to comply with the requirements of the bidding documents.

Notes on Standard Form of Letter of Acceptance The Letter of Acceptance will be the basis for formation of the Contract as described in Clauses 26 of the Instructions to Bidders. This Standard Form of Letter of Acceptance should be filled in and sent to the successful Bidder only after evaluation of bids has been completed.

### Standard Form C:	Letter of Acceptance

[letterhead paper of the DRC]

[date]

To:________________________________________________________________________

[name of the Contractor]

_________________________________________________________________________

[address of the Contractor]

This is to notify you that your Bid dated ___________for execution of the [name of the Contract and identification number, as given in the Contract Data] for the Contract Price of (_________________) [amount in numbers and words] __________________ [name of currency], as corrected and modified in accordance with the Instructions to Bidders is hereby accepted by Danish Refugee Council.

You are hereby instructed to proceed with the execution of the said Works in accordance with the Contract documents.

________________________

Authorized Signature: __________________________________________________________

Name and Title of Signatory: ___________________________________________________

Name of Agency_____________________________________________________________

Attachment: Agreement

Notes on Standard Form of Agreement The Agreement should incorporate any corrections or modifications to the Bid resulting from price corrections and price adjustment during the evaluation process as provided for in the Instructions to Bidders.

### Standard Form D:	Agreement

Agreement

This Agreement, made the __________________ day of _______________________ 2016, between __________________________________________________________________________________________________________________________________________________________________________________________[name and address of DRC] (hereinafter called “the DRC”) and ___________________________

_____________________________________________________________________________________________________________________________________________ [name and address of Contractor] (hereinafter called “the Contractor”) of the other part.

Whereas the DRC is desirous that the Contractor execute _________________ ______________________________________________________________________________ [name and identification number of Contract] (hereinafter called “the Works”) and the DRC has accepted the Bid by the Contractor for the execution and completion of such Works and the remedying of any defects therein.

Now this Agreement witnesseth as follows:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.

2.	In consideration of the payments to be made by the DRC to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the DRC to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

3.	The DRC hereby covenants to pay the Contractor in consideration of the execution and completion of the Works and the remedying of defects wherein the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

In Witness whereof the parties thereto have caused this Agreement to be executed the day and year first before written.

The Common Seal of __________________________________________________________________________ __________________________________________________________________________was hereunto affixed in the presence of:

Signed, Sealed, and Delivered by the

said ______________________________________________________________________ in the presence of:

Binding Signature of DRC ________________________________________________

Binding Signature of Contractor ___________________________________________

### Standard Form E:	Bid Security Form

Whereas [name of the Bidder] (hereinafter called “the Bidder”) has submitted its bid dated [date of submission of bid] for the supply of [name and/or description of the works] (hereinafter called “the Bid”).

KNOW ALL PEOPLE by these presents that we [name of bank] of [name of country], having our registered office at [address of bank] (hereinafter called “the Bank”), are bound unto [name of Purchaser] (hereinafter called “the Purchaser”) in the sum of for which payment well and truly to be made to the said Purchaser, the Bank binds itself, its successors, and assigns by these presents.  Sealed with the Common Seal of the said Bank this _____ day of ____________.

THE CONDITIONS of this obligation are:

1.	If the Bidder withdraws its Bid during the period of bid validity specified by the Bidder on the Bid Form;

or

2.	If the Bidder, having been notified of the acceptance of its Bid by the Purchaser during the period of bid validity:

(a)	fails or refuses to execute the Contract Form, if required; or

(b)	fails or refuses to furnish the performance security, in accordance with the Instructions to Bidders;

we undertake to pay to the Purchaser up to the above amount upon receipt of its first written demand, without the Purchaser having to substantiate its demand, provided that in its demand the Purchaser will note that the amount claimed by it is due to it, owing to the occurrence of one or both of the two conditions, specifying the occurred condition or conditions.

This guarantee will remain in force up to and including thirty (30) days after the period of bid validity, and any demand in respect thereof should reach the Bank not later than the above date.

[signature of the bank]

### Standard Form F:	Performance Security Form

To: [name of Purchaser]

WHEREAS [name of Supplier] (hereinafter called “the Supplier”) has undertaken, in pursuance of Contract No.  [reference number of the contract] dated ____________ to supply [description of works] (hereinafter called “the Contract”).

AND WHEREAS it has been stipulated by you in the said Contract that the Supplier shall furnish you with a bank guarantee by a reputable bank for the sum specified therein as security for compliance with the Supplier’s performance obligations in accordance with the Contract.

AND WHEREAS we have agreed to give the Supplier a guarantee:

THEREFORE, WE hereby affirm that we are Guarantors and responsible to you, on behalf of the Supplier, up to a total of [amount of the guarantee in words and figures], and we undertake to pay you, upon your first written demand declaring the Supplier to be in default under the Contract and without cavil or argument, any sum or sums within the limits of [amount of guarantee] as aforesaid, without your needing to prove or to show grounds or reasons for your demand or the sum specified therein.

This guarantee is valid until the _____ day of __________

Signature and seal of the Guarantors

[name of bank or financial institution]

[address]

[date]

# Section 6 	SPECIFICATIONS

These Notes for Preparing Specifications are intended only as information for the DRC or the person drafting the bidding documents. They should not be included in the final documents.

1.	A set of precise and clear specifications is a prerequisite for bidders to respond realistically and competitively to the requirements of the DRC without qualifying or conditioning their bids. In the context of competitive bidding, the specifications must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials, and performance of the goods and services to be procured. Only if this is done will the objectives of economy, efficiency, and fairness in procurement be realized, responsiveness of bids be ensured, and the subsequent task of Bid evaluation facilitated. The specifications should require that all goods and materials to be incorporated in the Works be new, unused, of the most recent or current models, and incorporate all recent improvements in design and materials unless provided otherwise in the Contract.

2.	Samples of specifications from previous similar projects in the same country are useful in this respect. The use of metric units is encouraged by the World Bank. Most specifications are normally written specially by the DRC to suit the Contract Works in hand. There is no standard set of Specifications for universal application in all sectors in all countries, but there are established principles and practices, which are reflected in these documents.

3.	There are considerable advantages in standardizing General Specifications for repetitive Works in recognized public sectors, such as highways, ports, railways, urban housing, irrigation, and water supply, in the same country or region where similar conditions prevail. The General Specifications should cover all classes of workmanship, materials, and equipment commonly involved in construction, although not necessarily to be used in a particular Works Contract. Deletions or addenda should then adapt the General Specifications to the particular Works.

4.	Care must be taken in drafting specifications to ensure that they are not restrictive. In the specification of standards for goods, materials, and workmanship, recognized international standards should be used as much as possible. Where other particular standards are used, whether national standards of the Borrower's country or other standards, the specifications should state that goods, materials, and workmanship that meet other authoritative standards, and which ensure substantially equal or higher quality than the standards mentioned, will also be acceptable. The following clause may be inserted in the Special Conditions or Specifications.

Sample Clause

Equivalency of Standards and Codes

Wherever reference is made in the Contract to specific standards and codes to be met by the goods and materials to be furnished, and work performed or tested, the provisions of the latest current edition or revision of the relevant standards and codes in effect shall apply, unless otherwise expressly stated in the Contract. Where such standards and codes are national, or relate to a particular country or region, other authoritative standards that ensure a substantially equal or higher quality than the standards and codes specified will be accepted subject to the DRC's prior review and written consent. Differences between the standards specified and the proposed alternative standards shall be fully described in writing by the Contractor and submitted to the DRC at least 28 days prior to the date when the Contractor desires the DRC's consent. In the event the DRC determines that such proposed deviations do not ensure substantially equal or higher quality, the Contractor shall comply with the standards specified in the documents.

# Section 7 	DRAWINGS

Insert here a list of Drawings. The actual Drawings, including site plans, should be attached to this section or annexed in a separate folder.

# Section 8 	BILL OF QUANTITIES

These Notes for Preparing a Bill of Quantities are intended only as information for the DRC or the person drafting the bidding documents. They should be included in the final documents.

In lump sum contracts, delete “Bill of Quantities” and replace with “Schedule of Activities” throughout this section.

| Objectives | 1. The objectives of the Bill of Quantities are (a) to provide sufficient information on the quantities of Works to be performed to enable bids to be prepared efficiently and accurately; and (b) when a Contract has been entered into, to provide a priced Bill of Quantities for use in the periodic valuation of Works executed. 2. In order to attain these objectives, Works should be itemized in the Bill of Quantities in sufficient detail to distinguish between the different classes of Works, or between Works of the same nature carried out in different locations or in other circumstances which may give rise to different considerations of cost. Consistent with these requirements, the layout and content of the Bill of Quantities should be as simple and brief as possible. |
| --- | --- |

| Day-work Schedule | 3. A Day-work Schedule should be included only if the probability of unforeseen work, outside the items included in the Bill of Quantities, is high. To facilitate checking by the DRC of the realism of rates quoted by the bidders, the Day-work Schedule should normally comprise the following: (a) A list of the various classes of labour, materials, and Constructional Plant for which basic day-work rates or prices are to be inserted by the Bidder, together with a statement of the conditions under which the Contractor will be paid for work executed on a day-work basis. |
| --- | --- |
|  | (b) Nominal quantities for each item of Day-work, to be priced by each Bidder at Day-work rates as Bid. The rate to be entered by the Bidder against each basic Day-work item should include the Contractor's profit, overheads, supervision, and other charges. |

| Provisional Sums | 4. A general provision for physical contingencies (quantity overruns) may be made by including a provisional sum in the Summary Bill of Quantities. Similarly, a contingency allowance for possible price increases should be provided as a provisional sum in the Summary Bill of Quantities. The inclusion of such provisional sums often facilitates budgetary approval by avoiding the need to request periodic supplementary approvals as the future need arises. Where such provisional sums or contingency allowances are used, the Contract Data should state the manner in which they will be used, and under whose authority (usually the DRC's). 5. The estimated cost of specialized work to be carried out, or of special goods to be supplied, by other contractors (refer to Clause 8 of the Conditions of Contract) should be indicated in the relevant part of the Bill of Quantities as a particular provisional sum with an appropriate brief description. A separate procurement procedure is normally carried out by the DRC to select such specialized contractors. To provide an element of competition among the bidders in respect of any facilities, amenities, attendance, etc., to be provided by the successful Bidder as prime Contractor for the use and convenience of the specialist contractors, each related provisional sum should be followed by an item in the Bill of Quantities inviting the Bidder to quote a sum for such amenities, facilities, attendance, etc. |
| --- | --- |