DRC

Terms of Reference (TOR)

for

Training Associate for the ASPIRE project

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and  supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

The overall purpose of this consultancy is creating and facilitating three ethnographic training modules for field researchers.

This will be done by designing a training package for a basic introduction to ethnography ethnographic field research methodology, tailored to the needs of the field researcher team (6-8 South Sudanese refugees from Rhino Camp Refugee Settlement in Uganda).

In addition, a report will be prepared on the initial training module. The report will (1) evaluate the first part of the training process in Uganda and provide recommendations on the further implementation of the training of the field researchers in Uganda. Moreover, (2) the report will detail recommendations on how to adapt the training module to the contexts of South Sudan and Kenya, where the training will be implemented in phase 2 (2024).

# Background

ASPIRE is a unique and progressive research project developed in as a partnership between DRC and  UNHCR. It follows a generation of young refugees in five different countries over a period of 15 years, exploring how they perceive and pursue opportunities for peace in their communities from their point of view. The overall objective of ASPIRE is to provide in-depth new knowledge about how young people, affected by the civil war(s) in South Sudan, over time, contribute to peaceful coexistence in their communities. Simultaneously, the research investigates how interventions by humanitarian actors are used by - and influence - the young people in their trajectories and practices. The research will be implemented alongside UNHCR’s Regional Youth Peacebuilding Project (RYPP), in five of the locations where it is currently active: Rhino Camp Refugee Settlement (Uganda), Kakuma Refugee Camp (Kenya), and among South Sudanese refugees Ethiopia, Sudan and returnees in South Sudan. This will allow the research to capture the effects of this important work as it takes place.

# Objective of the consultancy

The objective of this consultancy is to prepare, design and facilitate trainings for 6-8 field-based researchers in Uganda and to prepare the training of a similar number of field researchers in South Sudan and Kenya. By the end of the training, the field researchers are supposed to be familiar with basic concepts of ethnography and basic ethnographic methodology including participant observation, writing, managing and sharing ethnographic field notes, open-ended interview techniques and reflecting on the ethnographic data.

The consultant will be required to develop a training package with the following components and learning objectives:

- Introduction to the Aspire project and its methods and objectives

- A basic introduction to ethnography

- An introduction to ethnographic methods

  - participatory research (how, what are its strength, which data, to which end?)

  - field notes and research diary (why, when, how, what is enough?)

  - ethnographic (semi structured) interviews (why, when, how, what, what is enough?)

  - ‘lateral methods’ such as gathering testimonies from ones network (why, when, how, what, the difference to traditional ethnographic research methods)

  - longitudinal case studies (why, when, how, what - how are they distinct from the other methodological approaches?)

- Possibilities and challenges of ‘lateral’ research techniques (in one’s network)

- Possibilities and challenges of longitudinal research (case studies)

- Data management (securing, anonymizing, indexing…) and research ethics

- Collaboration within the research group (objectives, techniques, rights and responsibilities)

- Evaluation and feed-forward

The consultant will be required to co-facilitate the training with the PM, with the following components:

Sections 1 and 2 of TM1 are co-facilitated with the PM, as are parts of sections 3, 4 and 7

The consultant will be required to develop a report based on learning from the training with recommendations for follow-up trainings and how to adapt the package to future trainings in Phase 2 (South Sudan TM2 and Kenya TM3):

- Given, that the training package is new and untested, a review of its (partial) implementation in Uganda is a necessary first step (see section 2). An initial evaluation (with participating field researchers) is part of the first phase of the training package. A further evaluation with the PM will take place in Denmark.

- On the background of the initial experience with the training module (TM1) the further implementation of TM1 is discussed and an implementation plan is made.

- The initial TM1 will be adjusted both with regard to learned pedagogical lessons and with regard to country specifics.

The consultant will be required to adapt the training package based on the learning from the facilitation:

See previous sections

# Scope of work and Methodology

The Consultant will be required to prepare a detailed methodology and work plan indicating how

the objectives of the project will be achieved, and the support required from DRC.

# Deliverables

The Consultant will submit a field report based on the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1 Training development | Training development | - Training manual (for trainers) with education objectives and design - Training material (for trainees) | 10 working days |
| Phase 2 Facilitation | Facilitation workplan | Training Module 1 (TM1) workplan Day 1: arrival in Arua and coordination with PM Day 2: A) meeting with trainees & intro to training module; B) intro to ASPIRE Day 3: A) intro to ethnography; B) general into to ethnographic methods Day 4: A) participating research & field notes; B) interviews and lateral methods Day 5: One-day visit to camp A) introduction and short field exercise (participant observation); B) second field exercise (interviews) & discussion Day 6: A) research journal; B) reflexivity and auto-ethnography Day 7: A) case studies; B) evaluation and feed-forward | 7 working days |
| Phase 3 Reporting and adaption | Final report and final adaptation of training package | - Report on TM1, phase 1 - Recommendations for TM1, phase 2 - Reflections on TM1 for implementation of TM2 & TM3 - Training Manual and Training Material for TM2 and TM3 | 3 working days |

The Consultant will provide the documentation by email / Word, Excel, PowerPoint, PDF, etc.<

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 20 working days.

The consultant shall be prepared to complete the assignment no later than 30th September 2023

# Proposed Composition of Team

- Training Consultant

# Eligibility, qualification, and experience required

## Essential:

- Expertise in qualitative research methodology/ethnographic methodology

- Experience in conducting research with/via research assistants

- Experience with education design and implementation

Eligibility:

  - The consultant has the authorisation to work in Uganda

Qualification:

  - Educational level: Master or PhD

Experience:

  - A minimum of 5 years of conducting qualitative research proven. Teaching and facilitating ethnographic methodology.

Skills and knowledge:

- Qualitative research methodology/ethnographic methodology

  - (candidates selected for interviews will be invited to share example)

  - A solid understanding of the South Sudan context

Language requirements:

  - Written and spoken fluency in English

  - Working knowledge of Juba Arabic and indigenous languages is an advantage

# Technical supervision

The selected consultant will work under the supervision of:

- Programme Manager, Ayo Degett, ayo.degett@drc.ngo

# Location and support

Rhino Camp Refugee Settlement

The Consultant will provide her/his own computer and mobile telephone

# Travel

The consultant is expected to conduct 7 working days in the field.

The Consultant will therefore be expected to arrange transportation, accommodation, insurance, food and to make adequate provision in the Financial Proposal.

# Submission process

Please refer to the tender dossier

# Evaluation of bids

- Please refer to the tender dossier

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.