DRC

Terms of Reference (TOR)

for

Business Development & Fundraising Consultancy (ASPIRE)

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

The overall purpose of this consultancy is to position ASPIRE for funding opportunities in 2025 and beyond. This will be done by developing a fundraising strategy in close collaboration with the ASPIRE Fundraising Task Force, conduct a detailed mapping of relevant funding sources, prepare relevant concept notes with the ASPIRE team and start-up engagement with relevant donors and institutions.

Background

ASPIRE is a unique and progressive research project developed in as a partnership between DRC and UNHCR which started in 2023. It follows a generation of young refugees in five different countries over a period of 15 years, exploring how they perceive and pursue opportunities for peace in their communities from their point of view. The overall objective of ASPIRE is to provide in-depth new knowledge about how young people, affected by the civil war(s) in South Sudan, over time, contribute to peaceful coexistence in their communities. Simultaneously, the research investigates how interventions by humanitarian actors are used by - and influence - the young people in their trajectories and practices. The research will be implemented alongside UNHCR’s Regional Youth Peacebuilding Project (RYPP). In 2023, year 1, ASPIRE started its implementation in Rhino Camp Refugee Settlement (Uganda) and in year 2, the research project will be extended to Kakuma Refugee Camp (Kenya).

# Objective of the consultancy

The objective of this consultancy is to support the process of securing funding for ASPIRE beyond December 2024. This is a hands-on assignment that requires more than advising. The consultant is expected to draft simple concept notes and deliver comprehensive inputs to start/advance engagements with donors.

# Scope of work and Methodology

The consultant is required to:

- Develop a funding strategy and identify potential funding opportunities and corresponding business development needs of ASPIRE, for which DRC and/or UNHCR meet the funding eligibility criteria;

- Produce a draft mapping analysis of relevant donors and funding opportunities exists, building on the previous mapping conducted by DRC;

- Develop a capacity statement, a concise document that outlines ASPIRE’s capabilities, strengths, and qualifications.

- Develop and draft generic and activity-specific Concept Notes for general use with potential donors;

- Provide advice and light administrative support for donor engagement/communications, including by identifying donor strategic priorities and appropriate contact points and briefing management team and/or Fundraising Task Force team members; and

- Report progress regularly back to the ASPIRE Fundraising Task Force and HQ team.

# Deliverables

The Consultant will submit a field report based on the following deliverables as mentioned below. All deliverables will involve a planning-meetings and briefing-meeting with the Programme Manager to ensure expectations are aligned:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1 Review | Mapping Analysis & funding strategy | A funding strategy and mapping analysis with donor profiles, call(s) for proposals details, deadlines, and other business development needs. This will include a timeline and list of deliverables/resources and engagements needed to proceed with potential possibilities. It would require a ‘scenario’ approach where different funding scenarios would inform different approaches and ‘versions’ of ASPIRE. This mapping is expected to be extensive and cover comprehensively opportunities and stakeholders at global, regional and country level, and traditional and non-traditional donors, in all countries of implementation. | 10 days |
| Phase 2 Analysis | Capacity Statement | ASPIRE’s capacity statement will be a concise document that outlines its capabilities, strengths, and qualifications. It will serve as a marketing tool to showcase our capacity and suitability for receiving funding or grants from donors, foundations, government agencies, or other funding sources. | 1 day |
|  | General Concept Note | General concept note for use in a wide range of donor relations, including project overview, objectives and tangible results/targets, and relevance to global research, participation and peacebuilding priorities. | 7 days |
| Phase 3 Reporting | Activity-Specific Concept Notes (4) | Four activity-specific concept notes that isolate particular activities/costs of the programme for support by smaller-dollar value donors (e.g. private foundations, private sector partners, etc.) | 12 days |

The Consultant will provide the documentation by email / Word, Excel, PowerPoint, PDF, etc.

# Duration, timeline, and payment

Approx. 30 working days (one working day = 8 hours)

# Eligibility, qualification, and experience required

## Essential:

- Eligibility:

  - Technical Requirements: Access to a reliable and high-speed internet connection to support remote communication, research, and collaboration.

  - Remote Work Experience: Demonstrated experience in successfully completing remote consultancy assignments, showcasing the ability to work independently and meet deadlines without direct in-person supervision.

  - Own Equipment: Possession of a personal computer or laptop with updated software and necessary applications for remote work.

- Qualification:

  - Educational level: degree in a relevant field such as International Development, Business Administration, Fundraising Management, Peace and Conflict Studies, or a related discipline.

- Experience:

  - Proven success in fundraising for research programmes (academic and applied research).

  - Experience in business/programme development for international humanitarian organisations, especially for institutional and large private donors

  - Proven success in acquiring grants and funding for projects similar to ASPIRE.

  - Experience with peacebuilding funding is an advantage.

  - Proven experience in acquiring grants in the South Sudan/Sudan/Great Lakes/East Africa context.

- Skills and knowledge:

  - Proficiency in drafting high-quality proposals, grant applications, and program descriptions, showcasing a keen understanding of donor requirements and expectations.

  - Supporting communications with institutional and large private humanitarian, development and/or peacebuilding donors

  - Knowledge of the funding landscape for international humanitarian and peacebuilding projects, with a focus on staying informed about emerging trends, opportunities, and challenges.

- Language requirements:

- Excellent written and spoken fluency in English, with the ability to articulate complex ideas clearly and concisely.

# Technical supervision

The selected consultant will work under the supervision of:

- Programme Manager, Ayo Degett, ayo.degett@drc.ngo

# Location and support

The Consultant will provide her/his own computer, Wi-Fi connection and mobile telephone. The consultancy will be conducted remotely.

# Travel

Consultancy will be conducted remotely/no travel required. For HQ-based consultants

# Submission process

Please refer to the Invitation Letter.

# Evaluation of bids

- Please refer to the Invitation Letter.