DRC

Terms of Reference (TOR)

for

Global scoping study and guidance on the inclusion of LGBTQI+ persons in DRC´s GBV prevention and response and legal aid programming

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Objective and purpose of the Consultancy

The objective of this consultancy is to document existing external and DRC practices, guidance and tools on inclusive GBV prevention and response and legal aid programming and to develop DRC specific programme guidance that can be used by DRC`s GBV and legal aid staff.

The consultant will conduct a scoping study on existing DRC and external practices, guidance and tools for inclusive programming for LGBTQI+ persons and based on the study develop 2 new guidance documents for DRC´s GBV and Legal Aid programming.

# Background

This consultancy is based at The Danish Refugee Council - Global Protection Unit, Department for Strategy, Programme and Learning (SPL) and aims to further operationalize DRC´s Age, Gender & Diversity Mainstreaming Policy in which DRC commits to ensuring access to protection and assistance for at-risk and marginalized groups and ensuring that such assistance is appropriate and in accordance with their needs. Moreover, it builds on DRC´s global Gender-Based Violence (GBV) Policy which sets direction for DRC’s GBV interventions aimed at preventing and responding to situations of violence, coercion, deliberate deprivation and abuse that target women, girls, men and boys, as well as non-binary individuals and individuals with diverse sexual orientations. It also builds on DRC´s 2025 Strategy and strategic programme initiative on Expanding access to legal aid to the most vulnerable.

Evidence from DRC`s country operations show that LGBTIQ+ persons in humanitarian contexts often face discrimination, and violence when seeking protection and access to services. While several DRC country operations assist LGBTIQ+ persons, their needs and risks are not always identified in needs assessments or included in GBV prevention and response and legal aid programming due to lack of tailored approaches, clear guidance on how to reach and identify the specific risks and needs of this group and how to design and implement tailored approaches to address these. In some contexts, working with this group is also a sensitive matter that requires a protection-sensitive approach.

The consultant will under the supervision of the Strategic lead for DRC`s organizational principle 5 of DRC´s 2025 Strategy/Global Protection Advisor and global AGDM focal point, develop 1 scoping study and 2 DRC guidance documents on the inclusion of displaced LGBTIQ+ persons in DRC´s GBV and legal aid programs.

# Scope of Work

DRC seeks proposals from a consultant to conduct desk research on existing external and DRC GBV prevention and response and legal aid programming guidance on the inclusion of LGBTQI+ persons in humanitarian contexts. Specifically, the consultant will be tasked with developing 1 global scoping study on existing external and DRC (internal) practices, guidance and tools. The scoping study will inform the development of 2 new guidance documents and related tools for DRC staff, 1 for GBV staff in line with DRC`s existing Global GBV Policy, and 1 for legal aid staff in line with DRC´s Global Legal Aid Resource Pack. To fulfil the above objectives, the consultant will be required to deliver the following outputs.

- Scoping report (max 25 pages): Review and identify good practices and gaps in existing external and DRC (internal) programme guidance for inclusion of LGBTQI+ persons in GBV prevention and response and legal aid.

  - Conduct desk-based research on current external guidance available and tools on GBV and Legal Aid inclusive programming for LGBTQI+ population. The report should identify best practices and gaps for GBV prevention and response and Legal Aid programming in humanitarian settings and make recommendations for future research, advocacy and programming.

  - In consultation with DRC´s regional and country offices, the Consultant will map current GBV and Legal Aid LGBTQI+ inclusive programming, guidance and tools used by DRC country operations. The mapping should include online key informant interviews and/or focus group discussions with relevant DRC protection staff (legal aid and GBV) covering all DRC regions (Asia, Europe, Middle East, East Africa, West Africa and Latin America.) The report should identify good practices, gaps, and opportunities for cross-learning between operations and make recommendations for DRC´s global guidance.

- 2 Guidance documents and related tools on inclusive GBV prevention and response and legal aid programming.

  - Should provide practical and operational guidance to offices on how to design and implement LGBTQI+ inclusive GBV prevention and response and legal Aid programming and include examples of good practices from external organizations and DRC operations.

  - Should be developed in line with DRC`s current programmatic and protection guidance and tools as annexes, in particular DRC`s Global GBV policy and Global Legal Aid Resource Pack.

Methodology

The consultant should conduct desk-based secondary data review and primary data collection by engaging with DRC´s Regional and relevant Country Protection Coordinators and GBV and legal aid specialists in Asia, Europe, Middle East, East Africa, West Africa and Latin America to identify current practices and tools and to better understand operational gaps and needs. This should include online key informant interviews and/or focus group discussions.

# Deliverables

The consultant is responsible for the satisfactory delivery of all outputs outlined below.

| Phase | Deliverables | Indicative description tasks | Maximum Expected timeframe |
| --- | --- | --- | --- |
| Phase 1: Review of existing external practices and guidance | Scoping report identifying existing guidance and tools as well as gaps | Induction meeting with DRC-GPU, familiarization with DRC´s global policies, guidance and tools and development of an inception report on the scoping study outlining methodology and a time plan. | 3 days |
|  |  | Desk review of existing external and internal practices, guidance and tools. | 5 days |
|  |  | Key informant interviews/Focus Groups with DRC colleagues in regional and country offices | 8 days |
|  |  | Drafting of scoping report, identifying existing practices, guidance and tools, as well as gaps, and make recommendations for the programme guidance. | 8 days |
|  |  | Revisions based on feedback on report from DRC (allow for up to 10 working days for DRC to review). | 3 days |
|  |  | Presentation of scoping study to DRC-GPU, highlighting key findings and recommendations. | 0.5 day |
| Phase 2: Development of DRC guidance | DRC global guidance and tools | Drafting of guidance documents and related tools. | 10 days |
|  |  | Revision of guidance documents and tools based on feedback from DRC (allow for up to 10 working days for DRC to review). | 3 days |
|  |  | Presentation of final guidance documents and tools to DRC-GPU. | 0.5 day |
| Total number days |  |  | 41 days |

The deliverables from this consultancy should be delivered by email in English.

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 41 working days.

The consultant shall be prepared to complete the assignment no later than 1 December 2023.

| Deliverables | Due Date | Approved by | Payment |
| --- | --- | --- | --- |
| Inception report | 15 August 2023 | DRC | 10 % |
| Final version of Scoping report and presentation to DRC-GPU | 30 October 2023 | DRC | 40 % |
| Final version of Guidance documents and presentation to DRC-GPU | 1 December 2023 | DRC | 50 % |

# Proposed Composition of Team

# Applications from individuals or team of consultants will be accepted.

# Eligibility, qualification, and experience required

- Qualification:

- Master’s degree or equivalent in social sciences, development studies, or another related subject.

Experience:

- A minimum of 7 years of working experience in protection in humanitarian contexts.

  - At least 3 years in developing and implementing technical guidance on GBV and Legal Aid.

  - Experience of working with LGBTQI+ populations in displacement contexts.

Skills and knowledge:

- Expertise and previous experience in developing protection policies, guidance and research reports.

- Expertise in conducting social science research including strong analytical and drafting skills in English.

- Strong understanding of international protection standards and guidance, in particular on GBV prevention and response and Legal Aid.

- Previous experience in designing and implementing GBV prevention and response and/or Legal Aid programming for LGBTQI+ populations in displacement contexts.

- Excellent writing and communication skills.

- Ability to complete tasks efficiently and handling tight deadlines.

- Experience in design and delivery of interactive training materials and learning activities.

- Previous experience and knowledge of DRC´s protection work is considered an advantage.

Language requirements:

- Written and spoken fluency in English.

- Written and spoken fluency in Spanish, French and Arabic is an advantage.

# Technical supervision

The selected consultant will work under the supervision of the Global Protection Advisor, Joakim Daun, joakim.daun@drc.ngo.

# Location and support

This is a home-based consultancy no travel is expected for this consultancy.

# Travel

Not Applicable

# Submission process

Refer to the RFP letter of invitation.

# Evaluation of bids

Please refer to the RFP letter invitation.

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.