# Cash Consortium Yemen- CCY

# Impact Review Assessment

# Terms Of Reference-Annex F

## Introduction:

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

In the heart of Yemen's unyielding humanitarian crisis, the Cash Consortium Yemen (CCY) emerges as an unwavering force, bringing a spark of hope to the most vulnerable. Comprised of international non-governmental organizations (NGOs), the CCY unites under a common purpose: to provide vital cash assistance to those grappling with the harsh realities of conflict, displacement and natural disasters. By extending a lifeline of social safety net, the consortium addresses immediate needs and empowers vulnerable families to overcome unexpected shocks.

Pooling together their diverse expertise and resources, the CCY becomes a formidable humanitarian alliance, breaking barriers to reach even the most remote and isolated communities. The commitment to leaving no one behind is unwavering, as the consortium works tirelessly to ensure that aid reaches those who need it most. By focusing on cash assistance programs, the CCY seeks to alleviate suffering and instill a sense of dignity and autonomy in the recipients. The complexities of Yemen's crisis demand constant reassessment and innovative approaches, and the consortium remains steadfast in its mission. In the trial of Yemen's humanitarian turmoil, the CCY shines as a beacon of resilience and compassion, illuminating a path toward a better future for those who have endured so much.

The consortium was set up in 2020 and led by DRC together with ACTED, Norwegian Refugee Council (NRC), IOM (International Organization for Migration), Mercy Corps, and Solidarités International (SI). Until June 2023, the CCY has reached 11 governorates to support many displaced vulnerable households affected by natural calamities and protracted crisis.

This Evaluation Plan describes the evaluation activity of the programme, precisely the key considerations for each activity, including the purpose and scope, key evaluation questions, methodology, the selection of the evaluation team, the key audience, timeline, budget, coordination with other consortium partners and dissemination of findings and recommendations.

## SECTION I - ProGRAMME Overview

Building on the CCY partners' extensive experience in cash-based transfer programming within Yemen, the CCY proposes to a) provide MPCA as a first-line humanitarian response and b) support longer-term assistance to address more protracted needs by employing a strong referrals network to open pathways for vulnerable populations to access a wide range of services. The MPCA beneficiaries targeted under this award will include socio-economically vulnerable Yemeni IDPs, returnees, refugees, host communities, and those most affected by food insecurity and epidemic outbreaks. This proposed activity directly supports the Yemen 2021 Humanitarian Response Plan Yemen and its focus on ensuring maximal coverage of the most urgent, life-saving assistance integrated with a longer-term perspective.

a)	Goal: To increase the ability of vulnerable conflict-affected populations of Yemen to build stable foundations through addressing the most acute humanitarian needs and linking humanitarian and social protection programming.

b)	Theory of Change Statement: The proposed Theory of Change (ToC) states that: if individuals have access to food, essential services, non-food items and dignified shelter, if cash flow is increased in local markets, if the political, security and protective environment remains conducive, and if sequencing of humanitarian and development efforts is facilitated, then conflict-affected and vulnerable communities become more resilient and are better able to cope with shocks and crises.

c)	Purpose of Program: To improve the dignity and living conditions of affected populations in Yemen through harmonized, coordinated, timely, safe and accountable needs-based MPCA and linkages to longer-term assistance.

## SECTION II - Project Monitoring System

CCY Yemen has established a robust MEAL system to align with the country's context and meet the needs of stakeholders. The project ensures a continuous intake of beneficiaries by receiving numerous referrals from multiple agencies. CCY has devised its own criteria for selecting beneficiaries by assessing their vulnerability, food insecurity, coping strategies, and economic capacity to ensure eligibility and identify unique recipients.

To monitor the implementation and desired outcomes of the activity, the targeted beneficiaries undergo surveys for pre-assistance baseline, PDM, and endline evaluations. Remarkably, CCY maintains one of the largest beneficiary data warehouses in Yemen, making the program exceptionally cost-efficient by reducing duplicate assistance and specifically targeting the most vulnerable individuals. Additionally, the project utilizes software to keep track of outputs, ensuring efficient maintenance and monitoring throughout the process

## SECTION III- CCY LEARNING AGENDA

The Evaluation Plan highlights the interest of USAID and ECHO in expanding the knowledge base related to multipurpose cash assistance practices. The evaluations are intended to contribute valuable evidence to the decision-making process based on their Learning Agenda questions. These evaluations will align with the majority of USAID's learning agenda, with a specific focus on the following area:

- RESILIENCE TO SHOCKS: The evaluation will explore how CCY enhanced the resilience of households, communities, and the country against various challenges such as climate-related issues, conflicts, economic downturns, and health crises like COVID-19 and other global pandemics.

The research question from the Learning Agenda will be incorporated into the evaluations. CCY's program will concentrate on reinforcing the multipurpose cash transfer and implementing livelihood approaches for the affected community by 2024. The findings obtained from these evaluations will enable the consortium body and donors to gauge the extent to which cash assistance helped the beneficiaries build resilience against natural and man-made shocks and stressors.

## SECTION Iv- Purpose and SCOPES of the Evaluation

The main objective is to evaluate the program's performance against the desired results as articulated in the project's result framework. Specific objectives of the evaluations include:

- Assess whether the programme has adequately responded to the short, medium and long-term challenges as expressed in the project documents, including through expected synergies of a multipurpose cash assistant approach.

- Assess the overall project's performance from planning, implementation and knowledge management by identifying the key strengths and areas of gaps and make the necessary recommendations for future improvement

- Document vital lessons-learned, innovations/best practices resulting for future strategies and interventions

- Understand better what the project has achieved in relation to gender and disability and protection mainstreaming and overall results

- Support the use of relevant and timely contributions to organizational learning, informed decision-making processes resulting from the analysis, conclusions or recommendations as well as and accountability for results.

In order to achieve these objectives; will focus on the areas in Section V below:

## SECTION v- Criteria and Evaluation Questions to move forward:

| Criteria and Evaluation Questions | Sources of Information | Data Collection Tool |
| --- | --- | --- |
| Relevance and Coherence |  |  |
| - What extent are objectives of the project consistent with the beneficiaries' requirements, and needs? - Has the partnership approach been appropriate or effective? - Does the programme strategy and intervention package respond to the priority needs of displaced and crisis affected beneficiaries? | - Project documents - CCY staff - Government officials | - Literature Review - KIIs - IDIs |
| Effectiveness |  |  |
| - Are the projects' outputs and outcomes on track to be achieved in accordance with the stated plans? - Did the project's activities and outputs lead to the intended outcomes? - To what extent does the project implementation arrangement and strategies adequate for achieving expected results (budget structure, reporting lines, human resource allocation in line with project design?) - Are the program management strategies effective in delivering program plan and results? - Did the program/project contributing its intended outcomes, and what extent the result achieved by this time? | - Project documents - CCY staff - Partner NGO staff - Government officials | - Literature Review - KIIs - FGDs - IDIs |
| Efficiency |  |  |
| - Were activities implemented on schedule and within budget? - outputs delivered economically - How efficiently were the resources used to achieve the intended results in line with the implementation context? - How well are the resources (funds, expertise and time) being converted into results? | - Project documents - CCY staff - Partner NGO staff | - Literature Review - KIIs |
| Sustainability |  |  |
| - To what extent are the project activities connected to longer-term development concerns? - Are the benefits likely to be maintained for an extended period after assistance ends? - What is the likeliness of increased gender equality beyond the project end? | - Project documents - CCY staff | - Literature Review - KIIs |
| Impact (Early Signs of Impact) |  |  |
| - What changes did the project bring about against each outcome category? - Were there any unplanned or unintended changes? - To what extent will the gender-sensitive? | - Project documents - CCY staff - Partner NGO staff - Government officials | - Literature Review - KIIs - FGDs - IDIs |
| Cross-cutting Issues |  |  |
| - To what extent did the project design incorporate gender, person with disabilities? - What were the gender equality results and objectives achieved? Were gender mainstreaming principles adhered to by the project? - To what extent did the project adhere humanitarian protection principles in designing and implementing the project? | - Project documents - CCY staff - Partner NGO staff | - Literature Review - KIIs - FGDs - IDIs |

## SECTION VI - Key Evaluation Stakeholders and Users

Several internal and external stakeholders to CCY have interests in the evaluation results, and some stakeholders will be asked to play a role in the evaluation process. Those include CCY CMU, IOM, DRC RO Middle East, and CCY Partner agencies. Externally, USAID BHA, and ECHO would be two leading stakeholders funding this programme. Apart from those two, UNFPA, IRC, UNICEF, and WFP might find the evaluation interesting as beneficiary referral partners. Moreover, many sectors, for instance, RRM, CCCM, Cash and Market working group, Food and Nutrition, are involved with the CCY operationally and strategically. Government in Yemen and North (DFA) and South (IRG) are critically supporting this programme and might find the evaluation results meaningful.

## SECTION VII - Methodology for the evaluation

- The evaluation methodology will be aligned with OECD DAC criteria. It will be developed based on the requirements outlined in the TORs, along with further analysis conducted during the inception phase and consultations with key stakeholders. The evaluation team will collaborate to formulate an appropriate evaluation design, sampling strategy, and methodological approach, which will be documented in the Inception Report.

- The evaluation will utilize a mixed methods approach, incorporating both quantitative and qualitative elements. The quantitative survey design, sampling frame, and data collection methods will be informed by program coverage, context, and the list of indicators provided in the ITT. The design will ensure pre-post comparisons using baseline, endline, and final evaluation data. To enhance the methodology presented in the TOR, the Evaluation team will create an Evaluation Matrix during the Inception phase.

- The methodology for the baseline study and final evaluation will adhere to the following principles:

- Evaluation criteria of relevance, effectiveness, efficiency, impact, and sustainability will be applied.

- Impartiality and lack of biases will be demonstrated through the use of a diverse range of information sources, including different stakeholder groups, beneficiaries, etc. The selection of field visit sites will also reflect impartiality.

- An Evaluation Matrix will be employed to address key evaluation questions while considering data availability challenges, budget constraints, and timing constraints.

- The use of mixed methods will ensure the participation of women, girls, men, and boys from various stakeholder groups, and their perspectives will be incorporated into the evaluative outputs.

- Data collection methods will include a desk review, quantitative survey, semi-structured interviews, focus groups, and observations during field visits. The results of the endline survey will inform the assessment of project impact in the final evaluation.

- Quantitative techniques will primarily be used for data collection from different categories of beneficiaries in the baseline and endline surveys. Qualitative methods will be used to the extent possible and practicable to ensure triangulation and clarification of findings.

- Key informant interviews and/or focus group discussions will target stakeholders such as USAID BHA, ECHO, CCY implementing partners, IOM, Cash and Market Working Group, DFA, and IRG representatives.

- The design of the study will be based on the principle of longitudinal analysis, which will form the foundation for the observational evaluation design. The difference in indicators' status will be examined by comparing the panel households.

CCY leaves the following aspects of the evaluation plan open-ended until the inception phase:

- Confirmation of evaluation questions;

- Type of surveys, anticipated survey participants, geographic locations

- Discussion of anticipated statistical analysis techniques

- What data will be used to measure which outcomes?

## SECTION VIII – ROLES AND RESPONSIBILITIES

In accordance with the impartiality provisions, the CCY MEAL Manager will assume the role of the evaluation manager, ensuring no direct involvement with the implementation body. This position will provide continuous support to the evaluator throughout the entire process, assisting in developing a robust methodology, establishing efficient data collection systems, and facilitating communication with stakeholders for interviews. The data collection process must be conducted independently by the evaluation agency, and whether it will be done remotely or in-person will be decided based on the security situation and necessary permissions.

The CCY Chief of Party will serve as the overall focal point for this evaluation, taking charge of initiating the selection process, connecting the evaluator with external stakeholders, and validating the final report. Meanwhile, the Regional MEAL Coordinator will provide additional support to the evaluation, ensuring alignment with DRC evaluation policies and protocols.

## SECTION IX – Quality Assurance and Quality Assessment

CCY has established clear quality standards for this evaluation, incorporating processes with built-in steps for Quality Assurance, along with providing Templates for evaluation products and Checklists for their review. The principles and criteria expected for this evaluation align with the OECD DAC criteria, ensuring a consistent and robust approach.

To enhance the quality of the final TOR and inception/evaluation report, the evaluation manager will provide recommendations, with the support of the CCY chief of party. Throughout the analytical and reporting phases, the evaluation manager, along with CCY MEAL, will be responsible for ensuring the data's quality, including validity, consistency, and accuracy.

The evaluation team can be assured of the accessibility of all relevant documentation within the framework of the directive on disclosure of information. This ensures transparency and enables the team to have access to necessary resources for conducting a comprehensive evaluation.

## SECTION X- Selection of the EvaluatoR

The evaluation for the CCY will be undertaken by a qualified and independent evaluation agency. The selction will include a competitive tender process. The evaluation agency will be selected according to the following criteria:

- The evaluation team will comprise a team leader and other national and international team members, as necessary, to ensure a complementary mix of technical expertise in the evaluation’s focus areas (resilience, cash assistance, food security, gender and protection, capacity development etc.). In addition to the core evaluation team, a local field team will be engaged to support the process of data collection.

- The education expert should have previous experience in evaluating cash assistance, food security, livelihood or resilience projects. Prior experience in evaluating ECHO and/or BHA projects is expected.

- The evaluator should have data collection provisions in Yemen.

- All team members will be independent consultants and will include a mix of international and host-country national consultants (if relevant) who will work jointly (remotely if travel restrictions are still in place) to deliver evaluation products

- The lead evaluator should have a minimum of five years of experience in impact evaluation, research, and survey design.

- The evaluation team should ideally have conducted baseline/mid-term/endline studies/evaluations within the framework of a programme evaluation.

- The team leader must also demonstrate strong leadership experience.

## SECTION XII – Budget AND Delivery Plan

The following is the delivery plan and Financial Proposals should cover line items as detailed in the table below :

| Date | PHASES |
| --- | --- |
| PREPARATION PHASE FOR OVERALL EVALUATION |  |
| November 2023 | Assign roles/responsibilities and establish Evaluation Committee (CCY) |
|  | Develop Terms of Reference (TORs) and budget (CCY) |
|  | Procure independent evaluation firm (CCY) |
| INCEPTION PHASE FOR EVALUATION |  |
| December 2023 | Desk review of key project documents (evaluation team) |
|  | Inception mission (evaluation team and CCY) |
|  | Prepare Inception Report including quantitative and qualitative data collection tools (evaluation team) |
| FINAL EVALUATION |  |
| From December 2023 to February 2024 | Inception: Update to original Inception Report as required, review of desk documents (evaluation team) |
|  | Data collection and analysis (evaluation team) |
|  | Present the preliminary findings |
|  | Draft and finalize final Evaluation Report (evaluation team with inputs from CCY evaluation committee) |
|  | Disseminate final evaluation findings to internal stakeholders |
|  | Disseminate final evaluation findings to external stakeholders |
|  | Prepare CCY Consortium Executive Committee response on the recommendations (CCY) |

## Duration, Timeline, and Payment

The total expected duration to complete the assignment will be no more than three months.The timelines are subject to be revised based on the onboarding of an external evaluator and discussion with DRC Yemen -CCY

- The payments will be provided in three installments. The first installment is 20% of the total bid to be disbursed after submission of acceptance of inception report. . In the event that the bidder failed to submit acceptable inception report,DRC at its discretion might decide to terminate the contract and only payment up to Maximum 10% might be paid.

- The second installment is 30% after Presenting the preliminary findings .

- The third and final  installment 50% is to be paid after submition of final accepted report.

## SECTION XIII – Deliverables

- A detailed inception report with evaluation questions, methodology, link between the evaluation questions and methodology with rationale, timeline, data collection methods, analysis methods/theories etc.

- A brief of the preliminary results and findings to the evaluation committee

- A first draft report comprising the whole picture of the evaluation for review

- A final presentation to the stakeholders (CCY partner agencies and donors)

- Two final evaluation reports (short version, long version)

## SECTION XIV – Terms and conditions

- The payment installments entirely depend on handing over quality deliverables. If the expected quality is not produced, then CCY can terminate the contract with justifications

- The evaluation is expected to be completed within 3 months, however, if the situation requires the evaluator should remain flexible for short extensions to the timeline to deliver the products.

- CCY will not provide any visa, accommodation, or safety support to the evaluator or to the data collector team in Yemen. There are no payment provision aside from the amount budgeted for the assessment.

## SECTION XV-BIDS Technical Evaluation cRITERIA

| Technical criteria # | Technical criteria | Rating | TOTAL weighting to be awarded | RATING SCORES |
| --- | --- | --- | --- | --- |
| 1 | Bidder qualifications and experience | 1-10 | 60% |  |
| 1.1 | General capacity of the consultant - At least one team member has a bachelor's or master's degree in economics, statistics, social science or a relevant field. | 10 = Significantly above requirement 7 = Slightly above requirement 5 = Meets requirement 4 = Slightly below requirement 1 =Does not meet requirement | 10% | 1= No team member meets the requirement 4=One Team Members with Diploma Certificate 5=One Team Members with Bachelor’s degree 7= One Team member with Master Degree 10=Two Team Member with Bachelors or Master degree |
| 1.2 | Previous experience in evaluating BHA and ECHO project/programme | 10 = Significantly above requirement 7 = Slightly above requirement 5 = Meets requirement 4 = Slightly below requirement 1 =Does not meet requirement | 10% | 10 = 6 + ECHO and/or BHA projects 7 = Five ECHO and/or BHA projects 5 = Two to four ECHO and/or BHA projects 4 = One ECHO and/or BHA projects 1 =Does not have experience |
| 1.3 | At least one team member has a minimum of 5 years of experience handling project impact evaluations, thematic research The lead evaluator should have at least five years of experience in project | 10=Significantly above requirement 7=Slightly above requirement 5= Meet Requirements 4=Slightly below requirement 1= Doesn’t meet requirement | 10% | 1= One team member with zero years’ experience 4=One team member with one to four year experience 5= One Team member with 5 years’ experience 7=Two Team member with 5 years or more experience 10= Two team members with more than 5 years’ experience |
| 1.4 | Relevant sector experience doing similar evaluations for cash, livelihood and food security projects in emergency The consultant should have experience in evaluating at least two cash, or food security, or livelihood programs as well evaluating BHA and/or ECHO projects. | 10=Significantly above requirement 7=Slightly above requirement 5= Meet Requirements 4=Slightly below requirement 1= Doesn’t meet requirement | 20% | 1=No experience 4=One projects 5=Two projects 7=three to five projects 10= more than five projects |
| 1.5 | Experience in conducting impact evaluation or any assessment/research in Yemen The bidder should have at least two impact evaluation, or any assessment/research in Yemen and have data collection provision in Yemen. | 10=Significantly above requirement 7=Slightly above requirement 5= Meet Requirements 4=Slightly below requirement 1= Doesn’t meet requirement | 10% | 1=No experience 4= One assessment 5= Two to three assessments 7= Four assessment 10= Five or more |
| 2 | Proposed services (documented by the technical proposal) |  | 30% |  |
| 2.1 | Content of the proposal suitable for the requirements | 10=Significantly above requirement 7=Slightly above requirement 5= Meet Requirements 4=Slightly below requirement 1= Doesn’t meet requirement | 15% | 1=content of proposal doesn’t meet the requirements 4=content of the proposal suitable for only some requirements of the proposal contents required indicated in the TOR 5=Content of the proposal suitable for the requirements with moderate quality of presenting the proposed contents 7= content of the proposal suitable for all requirements with strong quality but lacks some aspacts 10= content of the proposal suitable for all requirements with strong quality and feasibility supported by practical and previous projects for all requirements including provision of past accepted projects for similar work with proving creativity and capacity to implement the required work indicated in the TOR |
| 2.2 | Proposed methodology to evaluate the evaluation objectives | 10=Significantly above requirement 7=Slightly above requirement 5= Meet Requirements 4=Slightly below requirement 1= Doesn’t meet requirement | 15% | 1=No suitable proposed methodology for the requirements 4=Proposed methodology not satisfying meeting the requirements 5=Proposed methodology moderately satisfied the requirements 7=Proposed methodology meets all requirements with better addition to improve the requirements 10=Proposed methodology exceeds the stipulated requirements for better professional improvement deliverable |
| 3 | Financial Capacity |  | 10% |  |
| 3.1 | Financial Capacity Bidder must submit documents to prove the financial capacity, such certified auditors' financial reports for the last 3 years. The annual volume/Annual Turnover of bidder for the past three years must be at least $100,000.00 | 10=Significantly above requirement 7=Slightly above requirement 5= Meet Requirements 4=Slightly below requirement 1= Doesn’t meet requirement | 10% | 1= Annual Turnover Less than $50,000.00 4= Annual Turnover from $50,000.00 to $99,000.00 5=Annual Turnover $100,000.00 7= Annual Turnover above $100,000.00 up to $150,000.00 10=Annual Turnover above $150,000.00 |

## sECTION XVI-Technical Supervision

The selected consultant will work under the supervision of CCY Department in DRC Yemen

## SECTION XVII-Location and Support

Flexibility to work remotely. But the data collection team should stay in Yemen and DRC will not pay anything extra regardless of the payments from the Evaluation

If travel is required, the consultancy firm will be responsible for its travel arrangements, accommodation and insurance.

The consultancy firm will utilise its own computers, mobile telephones, and graphics design tools, as required

## section xviii-Travel

Flexibility to work remotely. But the data collection team should stay in Yemen.The consultancy firm can work remotely under the technical supervision of focal persons listed in section (Technical Supervision). However, if travel is required it will be the sole responsibility of the consultant.