DRC

Terms of Reference (TOR)-Annex F

for

Consultancy support in producing the Mixed Migration Review (MMR) 2026

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and  supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

# Purpose of the consultancy

The Danish Refugee Council – Mixed Migration Centre based in Geneva, requires contribution of key content, procurement support and advisory input for the MMR 2026. The specific objectives, tasks and responsibilities and deliverables are listed below.

# Background

MMC is a knowledge centre engaged in data collection, research, analysis, and policy and programming on mixed migration. MMC has regional hubs hosted in Africa, Asia, Europe and Latin America, with a global team headquartered in Geneva, Switzerland, and based in several countries worldwide. MMC is a leading source for independent and high-quality data, research, analysis and expertise on mixed migration. MMC aims to increase understanding of mixed migration, to positively impact global and regional migration policies, to inform evidence-based protection responses for people on the move and to stimulate forward thinking in public and policy debates on mixed migration. MMC’s overarching focus is on human rights and protection for all people on the move.

Read more about the MMC here: www.mixedmigration.org. The MMC is part of the Danish Refugee Council.

Since 2018 MMC publishes the Mixed Migration Review (MMR), a review of mixed migration around the world focusing on key events and policy developments during the past year. The reports always include a series of essays looking at the most salient and polemical issues facing the refugee and migration sectors with respect to mixed migration, as well as a series of interviews with individuals and officials closely associated with or relevant to the sector and its challenges. The MMR is based on a wide range of secondary research as well as exclusive access to MMC’s 4Mi data. The report offers a deep analytical dive into the world of mixed migration. By offering a platform for debate and different voices, with this report the MMC aims to contribute to a more rational and less politicised analysis of mixed migration. Previous editions of the MMR are available here: http://www.mixedmigration.org/mmr/.

The MMR is MMC’s flagship and annual global report, directly contributing to two of MMC’s overall objectives: 1) To contribute to a better, more nuanced and balanced understanding of mixed migration (knowledge) and 2) To contribute to evidence-based and better-informed migration policies and debates (policy).

Since 2018 MMC has outsourced the overall management and production of the MMR. The MMR is made up of a large number of different components and usually includes around 20 different sub-contractors and procurements and payments (to essayists, proofreaders, essay competition winners, graphic designers, photo procurements, etc). To ensure that the production is efficient and provides value-for-money, MMC seeks the services of one provider highly familiar with the production of the MMR, to handle all procurement of subcontractors, as well as deliver high quality content for selected elements of the MMR.

# Objective of the consultancy

OBJECTIVES

- To provide high quality contributions for the Mixed Migration Review 2026.

TASKS AND KEY RESPONSIBILITIES

- Contribute to thematic brainstorming for the structure and themes of the MMR 2026, including overarching theme, essays, thematic snapshots, and expert interviewees.

In close communication with MMC:

- Conduct 10 interviews with mixed migration experts, producing finalized and publishable end products

- Produce 3 high-quality publishable articles for inclusion in the MMR

- Produce 1 high-quality essay

Procure and contract:

- High quality and thematically appropriate images

- MMR contributors including writers (e.g. essayists, alternative perspective prize winners, author(s) for keeping track, normalizing and resisting the extreme sections)

- External editor

- External proofreaders

- Layout designer

# Scope of work and Methodology

•	10 high quality, publishable interviews with mixed migration experts and thought leaders

•	3 high quality, publishable articles for inclusion in the MMR

•	1 high quality, publishable essay

•	16-20 thematically appropriate images

•	Procurement arrangements for 19 external MMR contributors

•	Participation in brainstorming discussions

# Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Task 1 | 10 high quality, publishable interviews with mixed migration experts | - Production of 10 selected interviews with mixed migration experts including devising questions, conducting interviews, collating transcripts and compiling a final version fit for publication | 17 working days |
| Task 2 | 3 high quality, publishable articles for inclusion in the MMR | - Production of 3 high quality short articles on global and emerging issues, for inclusion in the MMR 2026 (similar to some of the thematic snapshots in MMR2025) | 8 working days |
| Task 3 | 1 high quality, publishable essay | - The production of one essay 3500-5000 words on a topic chosen in collaboration with MMC, including the provision of an in-depth outline, a draft essay and a final essay incorporating any feedback from MMC | 12 working days |
| Task 4 | Selection and procurement of 16-20 thematically appropriate images | - To be selected based on discussions with MMC | 2 working days |
| Task 5 | Procurement arrangements for 19 MMR contributors | - Including devising and managing contracts and payments | 8 working days |
| Task 6 | Participation in brainstorming discussions | - 3-5 meeting with MMC regarding the thematic and strategic development of the MMR 2026 | 3 working days |

The Consultant will provide the documentation by email in one or all these formats: Word, Excel, PowerPoint, PDF.

# Duration, timeline, and payment

The total expected duration to complete the assignment will be working 50 days period between March and November 2026.

The consultant shall be prepared to complete the assignment no later than 30-11-2026.

PAYMENT

Payment 1: 1/3 at contract signature

Payment 2: 1/3 after 20 consultancy days with satisfactory performance and deliverables.

Payment 3: 1/3 after 30 consultancy days with satisfactory performance and deliverables.

# Proposed Composition of Team

- Project Manager

# Eligibility, qualification, and experience required

## Essential:

- Qualification:

  - Consultants should have a degree in Law, Social Sciences, Forced Migration or any other related area of study

- Experience:

  - Demonstrable experience on matters relating to mixed migration locally, regionally and globally.

  - A strong and proven background (e.g. through prior publications), knowledge and understanding of mixed migration dynamics.

- Skills and knowledge:

  - Proven research skills and experience in the area of forced migration and/or mixed migration.

  - Good understanding of legal and policy frameworks relating to migration.

  - Excellent analytical and reporting skills. Proven and strong track record of publications on mixed migration.

- Language requirements:

  - Fluency in written and spoken English.

Desirable:

- Previous successful collaboration with the MMC a strong asset

# Technical supervision

- The selected consultant will work under the supervision of Director of MMC

# Location and support

This is primarily a home-based consultancy. The Consultant will provide her/his own computer and mobile telephone.

# Travel

N/A

# Submission process

Please refer to the RFP letter invitation.

# Evaluation of bids

Please refer to the RFP letter invitation.