DRC

Terms of Reference (TOR)

for

Organizational development training services for diaspora organizations in Denmark

# Who is the Danish Refugee Council?

Founded in 1956, the Danish Refugee Council (DRC) is a leading international NGO and one of the few with a specific expertise in forced displacement. Active in 40 countries with 9,000 employees and supported by 7,500 volunteers, DRC protects, advocates, and builds sustainable futures for refugees and other displacement affected people and communities. DRC works during displacement at all stages: In the acute crisis, in displacement, when settling and integrating in a new place, or upon return. DRC provides protection and life-saving humanitarian assistance; supports displaced persons in becoming self-reliant and included into hosting societies; and works with civil society and responsible authorities to promote protection of rights and peaceful coexistence.

Via its Diaspora Programme, DRC has since 2010 engaged directly with diaspora actors to facilitate and strengthen their constructive engagement in support of persons affected by displacement and conflict. DRC recognizes diaspora as crucial transnational civil society actors playing a significant role, for people affected by displacement. Diasporas contribute to building resilience, responding to emergencies, and supporting early and long-term recovery. They are essential actors in support of durable solutions to displacement and in addressing root causes of displacement.

# Purpose of the consultancy

DRCs Diaspora Project Support in Denmark seeks proposals from consultants to deliver general and tailored individual capacity development services to selected diaspora associations in Denmark. The focus of the capacity development should be on organizational development of those associations that wish to, or already support recovery or development in their countries of origin.

# Background

One of the projects main projects in DRCs Diaspora Programme is the Danida-funded Diaspora Project Support (DiPS), through which DRC supports diaspora organisations in Denmark to conduct relief, rehabilitation and development activities in Somalia and Afghanistan, and to further enhance their capacities to function as diaspora civil society organisations.

# Objective of the consultancy

The purpose of this consultancy is to support the development and consolidation of diaspora civil society associations in Denmark, DiPS is seeking the services from one or more consultants to deliver general and tailor-made individual capacity development support to selected diaspora associations. The focus of the capacity development must be on the organizational development of those diaspora associations that wish to, or already engage with recovery or development activities in their countries of origin.

DiPS approves 9-13 grants per year to diaspora organizations. The offer for organizational development is voluntary, so we expect 2- 6 organizations per year to sign up for organizational development support. The number of sessions with each organization will be decided by the consultant in consultation with the DiPS team and is expected to be between three and five per organization. The above workload is an estimate.

# Scope of work and Methodology

With each of the selected organisations the consultant is expected to

- Develop a ‘resource check’ with each of the associations, which will guide the identification of gaps and issues that the subsequent training/coaching will focus on, and function as a baseline to measure impact.

- Based on the resource check, develop a plan for each organization to address their organisational priorities.

- Conduct training and coaching sessions with each organization in accordance with the plan.

- Evaluate the results of the organisational development processes.

- Produce a final report after the first year with common themes from the individual evaluations, main lessons learned, and recommendations for subsequent processes.

Ideally training and coaching sessions are held during the development and implementation of the DiPS-supported project with ample time in between to allow for the organizations to identify where to improve and have time to work on those issues. This is done recognizing that successful organizational change needs time and follow up.

We expect to continuously evaluate the set-up and add or decrease the support depending on needs and feedback from the diaspora organization. Continuous dialogue between the consultant and DiPS, as well as submission of a report with common themes from the individual evaluations, main lessons learned, and recommendations for subsequent phases should be submitted at the end of each year (end 2024 and end of 2025).

Other types of training within the same overall topic may be requested and agreed on between DRC and the selected consultant.

The total amount of training hours delivered as part of this assignment will depend on the number and types of requests received by the DiPS team and therefore no minimum number of hours can be guaranteed.

The diaspora organizations are driven by volunteers, so it is crucial that the selected consultant(s) is flexible in terms of availability and geography (some organisations are based in Jylland) and can conduct meetings outside of normal working hours.

# Deliverables

The Consultant will submit the following deliverables as mentioned below:

| Phase | Expected deliverables | Indicative description tasks | Maximum expected timeframe |
| --- | --- | --- | --- |
| Phase 1 | Resource checks for each participating association | Conduct initial sessions/exercises with the participating associations to identify gaps and issues that the subsequent training/coaching will focus on. The resource check will also function as a baseline to measure impact. | 5 hours per association |
| Phase 2 | A plan for training and coaching sessions | Based on the resource check, a training/coaching plan will be developed for each association. | 2 hours per association |
| Phase 3 | Training and coaching sessions | Joint training sessions on shared topics Individual training sessions / coaching with each association | Average 15 hours per association |
| Phase 4 | Evaluations | Individual evaluation sessions with each association | 2 hours per association |
| Phase 5 | Final report | Upon finalization of each year a final report must be submitted. | 15 hours in total |

The Consultant will provide the documentation by email and through follow-up meetings.

# Duration, timeline, and payment

The total expected duration to complete the assignment will be no more than 24 hours / three days per association.

The consultant shall be prepared to complete the assignment for the first batch of associations no later than 31.12.2024, and for the second batch of associations no later than 15.11.2025.

With reference to the above table with “Deliverables”, the full process for each organisation will consist of 24 hours of support.

Payments will reflect the number of associations, and the phases completed.

# Proposed Composition of Team

- Training consultant

# Eligibility, qualification, and experience required

## Essential:

- At least five years’ experience in similar training settings, preferably with diaspora or ethnic minority organizations in a Danish/European context;

- Demonstrated experience with training methodologies designed to strengthen volunteer and small-scale civil society organizations;

- Ability to work in a multicultural context as a flexible and respectful team player;

- Politically and culturally sensitive with qualities of patience, openness, and inclusion;

- Excellent Danish and English facilitation and writing skills are necessary.

# Technical supervision

The selected consultant will work under the supervision of:

- Anders.knudsen@drc.ngo

# Location and support

DRC office premises, or any other convenient location.

The Consultant will provide her/his own computer, mobile telephone, and other technical equipment needed.

        - DRC will support and cover costs related to venue bookings and refreshments for participants, and

        - Any other costs than those mentioned above should be factored in the daily rate.

# Travel

If travel outside of Copenhagen is required, DRC will, in consultation with the consultant, arrange or reimburse costs related to tickets and accommodation. Costs for travel should therefore not be part of the financial offer.

# Submission process

Please refer to the RFP invitation letter.

# Evaluation of bids

Please refer to the RFP invitation letter.

Only those shortlisted will be contacted for an interview with the panel to ensure their understanding of the consultancy services.